## ITP
INSPECTION & TEST PLAN
Quality Assurance Document
Project: |  |  | Contract No: |  |  | ITP Reference: |  |  |  | Revision:
General Title: |  |  | Work Package: |  |  | Date: |  |  |  | Page: | 1 of 1
Work By: |  |  | Drawing Nos / Doc Refs:
TEST & INSPECTION CODES
S |  |  | Record as diary entry — no notification required
I |  |  | Work continues — signed record required
W |  |  | Notification required — signed record if witnessed
H |  |  | STOP work until inspected and released — signed record
R |  |  | Review of documentation/records — signed record per package
O |  |  | Observation point — record sheet filled, no notification required
Op. No. | Operation to be Inspected or Tested | Controlled By (Position) | Accept / Reject Criteria | Frequency of Inspection or Test | Spec. Ref / Procedure or Method Statement | Records as Accepted | Sub- contractor | Contractor | Client | Designer |  | Notes / Comments
PRE-WORKS
1.0 | Review and approval of RAMS | Site Agent / Principal Contractor | RAMS authorised and signed off prior to works commencing | Prior to works | CDM 2015 Reg. 13 Site Safety Plan | Signed RAMS Permit to Work | H | H | R | O |  | Ensure all operatives briefed
1.1 | Design approval and drawing check | Design Engineer / Client Representative | Design compliant with specification and approved for construction | Prior to works | Contract specification Design drawings | Approved design package Design check certificate | O | H | H | H |  | Technical submission required
1.2 | Materials approval and certification | Materials Engineer / Site Agent | MAR approved — materials compliant with specification and certified | Prior to delivery | Contract spec. BS EN standards | Approved MARs Mill certificates Test reports | H | R | W | W |  | Includes factory test certs
1.3 | Existing services identification and protection | Site Engineer / Supervisor | All existing services located, marked and protected — permit to dig issued | Prior to excavation | HSG47 Site safety plan Utility records | Permit to Dig CAT & Genny records Service drawings | H | H | O | R |  | GPR survey if required
1.4 | Setting out and survey | Site Engineer | Setting out verified against design coordinates and levels | Prior to works per section | Design drawings Survey spec. | Setting out records As-set-out drawings Level sheets | W | H | O | W |  | Independent check required
1.5 | Environmental controls in place | Environmental Advisor / Site Agent | Pollution prevention measures, silt controls, and ecological constraints identified | Prior to works | CEMP Environmental permits BS 6031 | Environmental checklist Permit conditions | H | H | R | O |  | Check protected species
DURING WORKS
2.0 | Excavation and formation inspection | Site Engineer / Supervisor | Formation at correct level, stable, free from standing water and loose material | Each section / lift | Contract spec. BS 6031 Method statement | Formation inspection record Level survey | I | H | W | O |  | Photograph formation
2.1 | Bedding and surround material | Site Engineer / Supervisor | Correct material type, depth, and compaction as specification | Each pipe run / section | Contract spec. Series 500 Method statement | Compaction test results Material certificates | I | H | W | O |  | Compaction testing req'd
2.2 | Pipe / equipment installation | Site Engineer / Supervisor | Correct alignment, gradient, jointing — installed per manufacturer's requirements | Each unit / section | Manufacturer guidance Contract spec. Design drawings | Installation checklist Photographic record As-built survey | W | H | W | W |  | Jointing witnessed
2.3 | Concrete works — formwork, rebar and pour | Site Engineer / Supervisor | Formwork dimensions correct, rebar as design, concrete to spec — cube samples taken | Each pour | BS EN 206 BS 8500 Design drawings | Concrete pour record Cube test results Rebar inspection | W | H | W | H |  | Pre-pour checklist required
2.4 | Backfill and compaction | Site Engineer / Supervisor | Correct material placed in specified lifts, compaction to specification achieved | Each layer / section | Contract spec. Series 600 Method statement | Compaction test results Layer records | I | H | O | O |  | Nuclear density gauge
2.5 | MEICA installation and alignment | MEICA Engineer / Supervisor | Equipment installed per design, aligned, levelled, and secured — baseplate torques checked | Each item | Design drawings Manufacturer manual O&M requirements | Installation record Alignment report Torque records | W | H | W | H |  | Manufacturer rep on-site
2.6 | Welding and fabrication | Welding Inspector / Site Engineer | Welds to specification — visual and NDT inspection passed | Each weld / batch | BS EN ISO 5817 WPS / PQR Contract spec. | Weld log NDT reports Welder qualifications | W | H | W | H |  | IWE/IWT inspection
2.7 | Electrical installation and containment | Electrical Engineer / Supervisor | Cable routes, containment, terminations per design — safe isolation confirmed | Each circuit / zone | BS 7671 Design drawings Method statement | Electrical test certificates Installation records | W | H | W | H |  | NICEIC qualified
CLOSEOUT / REVIEW
3.0 | Pressure testing / leak testing | Site Engineer / Test Engineer | Test to specification — no leaks or pressure loss beyond tolerance over test period | Each system / section | Contract spec. WIS 4-01-03 BS EN 805 | Pressure test certificate Test records Photographic evidence | W | H | H | H |  | Client witness mandatory
3.1 | CCTV survey (where applicable) | CCTV Operator / Site Engineer | No defects, correct gradient, joints satisfactory — survey report acceptable | Each pipeline section | WRc SRM Contract spec. | CCTV survey report Defect schedule | R | H | W | O |  | WRc classification
3.2 | Commissioning and functional testing | Commissioning Engineer / Client | All systems tested and performing to design parameters — SAT/FAT complete | Each system | Commissioning spec. O&M manual Design criteria | Commissioning report SAT/FAT certificates Snagging list | W | H | H | H |  | Witnessed commissioning
3.3 | As-built survey and record drawings | Site Engineer / Surveyor | As-built drawings accurately reflect installed works — survey data submitted | On completion | Contract spec. Survey requirements | As-built drawings Survey data GIS records | R | H | R | H |  | CAD format required
3.4 | O&M manual and handover documentation | Document Controller / Agent | Complete O&M package submitted — all certificates, test results, and warranties included | On completion | Contract spec. CDM 2015 H&S file requirements | O&M manual H&S file Warranties Spare parts list | R | H | H | R |  | H&S file contribution
3.5 | Final inspection and defects walkdown | Site Agent / Client Representative | All works complete to specification — snagging items identified and programme agreed | On completion | Contract spec. Defects procedure | Snagging list Defects schedule Completion certificate | W | H | H | W |  | Joint inspection
APPROVAL & SIGN-OFF
Prepared By: |  |  |  |  | Checked By: |  |  |  | Approved By:
Signature: |  |  |  |  | Signature: |  |  |  | Signature:
Print Name: |  |  |  |  | Print Name: |  |  |  | Print Name:
Position: |  |  |  |  | Position: |  |  |  | Position:
Date: |  |  |  |  | Date: |  |  |  | Date:
S = Surveillance ¦ I = Inspection ¦ W = Witness Point ¦ H = Hold Point ¦ R = Records Review ¦ O = Observation

## CS — Pre-Works
CHECKSHEET — PRE-WORKS
Project: |  |  |  | Contract No:
ITP Reference: |  |  |  | Revision:
Location: |  |  |  | Area:
Drawing Ref & Rev: |  |  |  | RAMS (No. & Rev):
Op. No. | Inspection Item | Sub- contractor | Contractor | Client | Designer | Comments / Result
1.0 | Review and approval of RAMS
1.1 | Design approval and drawing check
1.2 | Materials approval and certification
1.3 | Existing services identification
1.4 | Setting out and survey
1.5 | Environmental controls in place
ACTIONS TO CORRECT NONCONFORMANCES:
ACCEPTANCE FOLLOWING WORK COMPLETION:
All nonconformances have been identified by NCRs and those necessary have been rectified satisfactorily. All snagging items have been resolved or adequately recorded.
Contractor: |  |  |  | Client:
Sign: |  |  |  | Sign:
Name: |  |  |  | Name:
Date: |  |  |  | Date:
S = Surveillance ¦ I = Inspection ¦ W = Witness Point ¦ H = Hold Point ¦ R = Records Review ¦ O = Observation

## CS — During Works
CHECKSHEET — DURING WORKS
Project: |  |  |  | Contract No:
ITP Reference: |  |  |  | Revision:
Location: |  |  |  | Area:
Drawing Ref & Rev: |  |  |  | RAMS (No. & Rev):
Op. No. | Inspection Item | Sub- contractor | Contractor | Client | Designer | Comments / Result
2.0 | Excavation and formation inspection
2.1 | Bedding and surround material
2.2 | Pipe / equipment installation
2.3 | Concrete works — formwork, rebar and pour
2.4 | Backfill and compaction
2.5 | MEICA installation and alignment
2.6 | Welding and fabrication
2.7 | Electrical installation and containment
ACTIONS TO CORRECT NONCONFORMANCES:
ACCEPTANCE FOLLOWING WORK COMPLETION:
All nonconformances have been identified by NCRs and those necessary have been rectified satisfactorily. All snagging items have been resolved or adequately recorded.
Contractor: |  |  |  | Client:
Sign: |  |  |  | Sign:
Name: |  |  |  | Name:
Date: |  |  |  | Date:
S = Surveillance ¦ I = Inspection ¦ W = Witness Point ¦ H = Hold Point ¦ R = Records Review ¦ O = Observation

## CS — Closeout
CHECKSHEET — CLOSEOUT / REVIEW
Project: |  |  |  | Contract No:
ITP Reference: |  |  |  | Revision:
Location: |  |  |  | Area:
Drawing Ref & Rev: |  |  |  | RAMS (No. & Rev):
Op. No. | Inspection Item | Sub- contractor | Contractor | Client | Designer | Comments / Result
3.0 | Pressure testing / leak testing
3.1 | CCTV survey
3.2 | Commissioning and functional testing
3.3 | As-built survey and record drawings
3.4 | O&M manual and handover documentation
3.5 | Final inspection and defects walkdown
ACTIONS TO CORRECT NONCONFORMANCES:
ACCEPTANCE FOLLOWING WORK COMPLETION:
All nonconformances have been identified by NCRs and those necessary have been rectified satisfactorily. All snagging items have been resolved or adequately recorded.
Contractor: |  |  |  | Client:
Sign: |  |  |  | Sign:
Name: |  |  |  | Name:
Date: |  |  |  | Date:
S = Surveillance ¦ I = Inspection ¦ W = Witness Point ¦ H = Hold Point ¦ R = Records Review ¦ O = Observation