## Cover
EBRORA
ebrora.com
ITP Pack Index
A complete index of all Inspection & Test Plan points, organised by discipline — track every Hold, Witness and Review point from issue to close-out.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — ITP Pack Index
Step-by-Step Instructions
1. | Go to the 'ITP Pack Index' sheet. Enter the Project Name and Contract Number in the info strip at the top.
2. | The sheet is organised into discipline sections, each introduced by a teal section header. Add new rows within the relevant discipline section.
3. | Each ITP item has a sequential Pack Ref (ITP-CV-001, ITP-ST-001, etc.) — enter this in column A, or use your project-specific ITP numbering.
4. | Enter the Activity or Inspection Point description in column B. This should match the ITP document exactly.
5. | Use the Classification dropdown in column C to set the inspection point type: Hold Point, Witness Point, or Review Point.
6. | Enter the Responsible Party in column D — typically the Contractor or Named Subcontractor responsible for notifying the inspection.
7. | Set the Required By date in column E — the date the inspection must be completed by (linked to programme).
8. | Update the Status dropdown (column F) as inspection points are progressed. The row colour updates automatically.
9. | Enter the Inspection Date in column G when the physical inspection takes place, and record the Inspector's name in column H.
10. | The subtotal row at the bottom of each section counts Closed points and calculates a section completion percentage. The grand total at the bottom summarises the whole project ITP status.
Colour Key
Teal section headers — Discipline group divider. Not a data row.
Closed — Inspection complete and accepted. Pack closed.
In Progress — Inspection notified or underway. Awaiting sign-off.
Overdue — Required By date has passed and the point is not yet closed.
Failed — Inspection carried out but the work did not pass. NCR action required.
Waived — Hold/Witness point formally waived by Employer's Representative.
Light teal cells — User input / editable fields.
Light teal subtotal rows — Auto-calculated section completion. Do not edit.
Tips
* | The ITP Pack Index is your quality audit trail backbone. At handover, every Hold Point must show a Closed status with an inspector name and date — otherwise the H&S file and O&M pack are incomplete.
* | For Witness Points, if the Employer's Representative does not attend within the agreed notice period (typically 24–48 hours), record 'ER Not in Attendance — Proceeded' in the Notes column. This protects you during any later quality challenge.
* | Use the section completion percentages at the bottom of each discipline group in your weekly quality report. A discipline section that is 100% closed is ready for handover. One at 60% needs active management.

## ITP Pack Index
Project Name: |  | [Enter Project Name] |  |  |  | Contract No: |  | [Contract No]
PROJECT ITP SUMMARY |  |  | TOTAL | -173 | CLOSED | 6 | HOLD PTS | 7 | WITNESS PTS | 3 | % COMPLETE | 50%
Pack Ref | Activity / Inspection Point Description | Classification | Responsible Party | Required By | Status | Inspection Date | Inspector | WIS Ref | NCR Ref | ITP Doc Ref | Notes | Sign-Off Ref
Section 1 — Civil & Structural Works
ITP-CV-001 | Formation Level Survey & Approval — Zone 3 Inlet Trench | Hold Point | Groundworks Ltd | 2025-01-10 | Closed | 2025-01-11 | J. Hargreaves | WIS-001 |  | ITP-CV Rev 2 | Survey cert attached. ER signed. | HP-CV-001
ITP-CV-002 | Blinding Concrete Placement — Primary Tank Base | Hold Point | Groundworks Ltd | 2025-01-15 | Closed | 2025-01-15 | J. Hargreaves | WIS-002 |  | ITP-CV Rev 2 | Level tolerance ±5mm confirmed. | HP-CV-002
ITP-CV-003 | Reinforcement Inspection — Tank Walls 1st Lift | Hold Point | Groundworks Ltd | 2025-01-24 | Closed | 2025-01-25 | S. Patel | WIS-003 |  | ITP-ST Rev 1 | Cover 50mm. Bar sizes verified. | HP-CV-003
ITP-CV-004 | Pipe Bedding & Laying — DN300 Inlet Main Zone 3 | Witness Point | Groundworks Ltd | 2025-02-06 | Closed | 2025-02-06 | T. Walsh | WIS-004 |  | ITP-CV Rev 2 | ER attended. Bedding depth confirmed. | WP-CV-001
ITP-CV-005 | Post-Concrete Cube Testing — Tank Base Pour | Review Point | Groundworks Ltd | 2025-02-10 | Closed | 2025-02-11 | S. Patel |  |  | ITP-CV Rev 2 | 28-day cube results: 48MPa. Pass. | RP-CV-001
ITP-CV-006 | Backfill Compaction Testing — Zone 3 Trench | Witness Point | Groundworks Ltd | 2025-03-05 | In Progress |  |  | WIS-008 |  | ITP-CV Rev 2 | Plate bearing test scheduled 05/03.
Section 1 Completion — | [5 empty] | 5 | 6 | 83.33%
Section 2 — Mechanical & Process Works
ITP-ME-001 | Pump Station Baseplate Setting & Grouting — PST-01 | Hold Point | Walsh MEP Ltd | 2025-03-10 | In Progress |  |  |  |  | ITP-ME Rev 1 | Grouting sequence agreed. Awaiting structural cure.
ITP-ME-002 | Pressure Test — DN300 Inlet Rising Main (PN16) | Hold Point | Walsh MEP Ltd | 2025-03-18 | Open |  |  |  |  | ITP-ME Rev 1 | Test pressure 24 bar. 1hr duration. ER to witness.
ITP-ME-003 | Valve Actuator Function Test — FCV-101, FCV-201 | Witness Point | Walsh MEP Ltd | 2025-04-02 | Open |  |  |  |  | ITP-ME Rev 1
Section 2 Completion — | [5 empty] | 0 | 2 | 0%
Section 3 — Electrical & Instrumentation
ITP-EL-001 | MCC Factory Acceptance Test (FAT) — MCC-01 | Hold Point | Roberts Electrical | 2025-02-28 | Closed | 2025-02-28 | C. Roberts |  |  | ITP-EL Rev 1 | FAT completed at manufacturer. Schedule attached. | HP-EL-001
ITP-EL-002 | Cable Installation Continuity & Insulation Tests — MCC-01 | Review Point | Roberts Electrical | 2025-04-10 | Open |  |  |  |  | ITP-EL Rev 1
ITP-EL-003 | SCADA Site Acceptance Test (SAT) — Full System | Hold Point | InControl Systems Ltd | 2025-05-15 | Open |  |  |  |  | ITP-EL Rev 1 | SAT procedure to be issued 6 weeks prior.
Section 3 Completion — | [5 empty] | 0 | 2 | 0%

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.