## Cover
EBRORA
ebrora.com
ITP (Inspection & Test Plan) Tracker
Track inspection and test plan activities with hold, witness, and review point management.
Stage-gate tracker with sign-off status, responsible parties, and completion monitoring.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. | Open the 'ITP Tracker' sheet. The dashboard shows completion rates by inspection type (Hold/Witness/Review).
2. | List each work activity or construction stage in the Activity column. Assign the inspection type: H (Hold Point), W (Witness Point), or R (Review Point).
3. | Hold Points (H) require mandatory sign-off before work proceeds. Witness Points (W) are optional — the inspector may choose to attend. Review Points (R) require document review only.
4. | For each activity, enter the responsible party (Contractor, Client, Third Party), the acceptance criteria, and the reference document.
5. | When an inspection is completed, enter the date, result (Pass/Fail/Conditional), and the inspector's name. Pass turns green, Fail turns red.
6. | The dashboard auto-counts inspections by status: Pending, Passed, Failed, and Conditional. Overall ITP completion % updates in real time.
7. | Use this alongside your quality management plan. Hold Points that are bypassed without sign-off are non-conformances.
Colour Key
Light teal — user input
Dark navy — headers
Green — Pass / completed
Amber — Conditional pass or Witness point (optional)
Red — Fail / Hold Point not yet released
Tips
• | Never proceed past a Hold Point without documented sign-off — this is the most critical quality control mechanism.
• | Issue the ITP to the client/supervisor at project start. Agree Hold and Witness Points before work begins.
• | Keep all inspection records filed with the ITP — they form part of the quality handover pack.

## ITP Tracker
INSPECTION & TEST PLAN (ITP) TRACKER
Project: |  | Example Infrastructure Project |  |  |  | ITP Ref: |  | ITP-2026-001
Completion Dashboard |  |  |  |  | Overall Progress
Pending: | 0 | Pass: | 0 |  | Total Items: | 12
Fail: | 0 | Conditional: | 0 |  | Completion: | 0%
ITP SCHEDULE
Activity / Work Stage | Inspection Type | Acceptance Criteria | Reference Document | Responsible Party | Contractor | Client | Inspection Date | Result | Inspector | NCR Ref | Remarks | Close-Out Date
FOUNDATIONS
Excavation to formation level | H — Hold Point | Formation level check ±25mm. No soft spots or water ingress. | Spec Section 3.2 | Joint | ✓ | ✓ | 2026-02-15 | Pass | T. Henderson |  | Formation approved. Photo record taken.
Blinding concrete placement | R — Review Point | Concrete grade C10, min 50mm thickness. | Spec Section 3.3 | Contractor | ✓ | — | 2026-02-16 | Pass | M. Khan
Rebar fixing — foundations | H — Hold Point | Rebar size, spacing, cover per drawing RC-101. Spacers at 1m centres. | Drawing RC-101 | Joint | ✓ | ✓ | 2026-02-20 | Pass | T. Henderson |  | Cover meter readings logged.
Concrete pour — foundations | W — Witness Point | C35/45, slump 100±25mm. Cube samples taken (3 per 50m³). | Spec Section 3.5 | Joint | ✓ | ✓ | 2026-02-22 | Pass | T. Henderson |  | Batch tickets on file. 6 cubes taken.
SUBSTRUCTURE
Waterproofing membrane installation | H — Hold Point | Type A membrane per BS 8102. Laps min 150mm. No damage. | Spec Section 4.1 | Joint | ✓ | ✓ | 2026-03-05 | Conditional | T. Henderson | NCR-007 | Minor lap defect at Grid B3. Repaired and re-inspected. | 2026-03-08
Backfill material approval | H — Hold Point | 6F2 material, compaction to 95% MDD. Layer thickness max 300mm. | Spec Section 4.3 | Contractor | ✓ | — |  | Pending
Drainage installation — below slab | W — Witness Point | Falls min 1:80. Joints sealed. CCTV survey before cover. | Drawing DR-201 | Joint | ✓ | ✓ |  | Pending
SUPERSTRUCTURE
Steel frame erection — alignment check | H — Hold Point | Plumb ±5mm per storey. Bolt torque per structural engineer spec. | Drawing S-301 | Joint | ✓ | ✓ |  | Pending
Concrete frame — rebar pre-pour | H — Hold Point | As per RC drawing series. Cover, spacers, laps per spec. | Drawing RC-301 | Joint | ✓ | ✓ |  | Pending

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.