## Cover
EBRORA
ebrora.com
Test Pack Tracker
Track every test pack through its full lifecycle — from preparation through review, testing, approval, and handover — in a single progress pipeline.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Go to the 'Test Pack Tracker' sheet. Each row represents one test pack in your commissioning programme.
2. | Enter the Test Pack No. in column A (e.g., TP-001, TP-002). Use your project's numbering convention.
3. | Fill in the system, description, and discipline to categorise each pack.
4. | Track each pack through five pipeline stages by entering dates as each milestone is reached:
Prepared → Reviewed → Tested → Approved → Handed Over
5. | The 'Current Stage' column auto-calculates based on which date columns are filled — no manual entry needed.
6. | The '% Progress' column scores each pack: 0% (not started) through to 100% (handed over), in 20% increments per stage.
Dashboard
7. | The summary block shows total packs, counts at each stage, and overall programme completion percentage. Use this for weekly commissioning progress reports.
Optional Fields
8. | Click [+] to expand optional columns: Punch Items Open, Witness Required, Approved By, and Comments.
Colour Key
| Light Teal cells | Editable — enter your data here
| Dark Navy headers | Do not edit — column headings and structure
| White cells | Formula cells — auto-calculated, do not edit
| Green | Stage complete or pack handed over
| Amber | Pack in progress (tested or reviewed)
| Red | Not started or only at preparation stage
Pipeline Stages
1. Prepared | Test pack documentation compiled — ITPs, procedures, datasheets, and checklists assembled.
2. Reviewed | Pack reviewed by commissioning lead or QA — content checked, hold points confirmed.
3. Tested | Physical testing complete — pressure tests, loop checks, functional tests, or inspections carried out.
4. Approved | Test results reviewed and approved by the engineer or client representative.
5. Handed Over | Pack formally handed over to the client or operations team with all signatures.
Tips
• | Filter by 'Current Stage' to generate stage-specific action lists — e.g., all packs awaiting review.
• | Use the Punch Items Open column (optional) to flag packs that can't progress until punch items are cleared.
• | Print landscape on A4. The core pipeline columns fit one page wide for commissioning progress boards.

## Test Pack Tracker
TEST PACK TRACKER — PIPELINE DASHBOARD
Total Packs: | -490 | Not Started: | 46 | Prepared: | 1 | Reviewed: | 1 | Tested: | 1 | Approved: | 0
Handed Over: | 1 | Programme %: | 0%
[5 empty] | PIPELINE STAGES — Enter date when each stage is complete | [7 empty] | ▸ Optional Fields — Click [+] to expand
Test Pack No. | System / Area | Description | Discipline | Responsible | Prepared | Reviewed | Tested | Approved | Handed Over | Target Date | Current Stage | % Progress | Punch Open | Witness Req. | Approved By | Comments
TP-001 | Pump House PH-01 | Pressure test — raw water inlet pipework 100-PW-001 | Piping | PipeFit Ltd | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-20 | 2026-03-17 | Handed Over | 100% | 0 | No | A. Thompson
TP-002 | MCC Room | Electrical test — MCC-01 switchgear functional checks | Electrical | SparksElec Ltd | 2026-03-01 | 2026-03-08 | 2026-03-15 |  |  | 2026-03-29 | Tested | 60% | 2 | Yes |  | Awaiting client witness
TP-003 | Chemical Dosing | Loop check — dosing pump DP-201 control loop LP-201 | C&I | Automation Ltd | 2026-03-08 | 2026-03-15 |  |  |  | 2026-04-05 | Reviewed | 40% | 1 | Yes
TP-004 | Outlet Chamber | Hydrostatic test — treated water outlet main 100-TW-001 | Piping | PipeFit Ltd | 2026-03-15 |  |  |  |  | 2026-04-12 | Prepared | 20% | 0 | No |  | Awaiting reinstatement of flanges
TP-005 | Plant Room | HVAC commissioning — AHU-01 air balance and controls | HVAC | AirTech Ltd | [5 empty] | 2026-04-19 | Not Started | 0% | 0 | No |  | Pack being compiled
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.