## Cover
EBRORA
ebrora.com
Material Verification Tracker
Record every material delivery, check it against specification, and track pass/fail outcomes and NCR actions — from first delivery to final sign-off.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — Material Verification Tracker
Step-by-Step Instructions
1. | Go to the 'Material Verification' sheet. Enter the Project Name and Contract Number in the info strip at the top.
2. | For each delivery, the Ref column (A) auto-generates a sequential reference (MVT-001, MVT-002, etc.) once a Description is entered.
3. | Enter the Delivery Date in column B and the material description in column C. Be specific — include product name, standard, grade and size.
4. | Record the Supplier name in column D and the Delivery Note (DN) or Order Number in column E.
5. | Select the Material Category from the dropdown in column F to allow filtering by material type.
6. | Enter the Specification Reference in column G — the drawing number, pipe class, mix design, or spec clause the material must comply with.
7. | Use the Verification Method dropdown in column H: Visual, Dimensional Check, Test Certificate, or Third Party Test.
8. | Set the Result (column I) to Pass or Fail based on your inspection. Fail triggers a red row highlight — raise an NCR immediately.
9. | If the result is Fail, record the NCR number raised in column J. Track the NCR to closure — the material must not be incorporated until resolved.
10. | Record who carried out the inspection in column K and any relevant notes in column L. Expand Optional Columns (M–P) for batch numbers, lab reports and file references.
Colour Key
Pass — Material checked and accepted. Compliant with specification.
Fail — Material does not meet specification. Do not incorporate. NCR required.
Pending — Awaiting test results, certificates or further review before a verdict can be given.
Rejected/Returned — Material formally rejected and returned to supplier.
Light teal cells — User input / editable fields.
Dark navy header rows — Do not edit.
Tips
* | A material verification check is not just about looking at what arrives — check the test certificate or conformity declaration against the specification. A CE-marked product is not automatically spec-compliant.
* | If a material fails verification, do NOT allow it to be offloaded or incorporated. Mark it clearly, segregate it from compliant stock, and raise an NCR on the same day. Late NCRs are a red flag during audits.
* | Keep a physical copy of delivery notes and test certs in the site quality file. This register is the index — the paper trail must back it up. Under NEC4, materials incorporated without verification can trigger a defect.

## Material Verification
Project Name: |  | [Enter Project Name] |  |  |  | Contract No: |  | [Contract No] |  |  |  | ▸ Optional Fields — Click [+] to expand
Ref | Delivery Date | Material Description | Supplier | DN / Order Ref | Material Category | Specification Reference | Verification Method | Result | NCR Ref | Inspected By | Notes | Batch / Heat No. | Test Cert Ref | Lab Report Ref | File Path / Link
MVT-001 | 2025-01-14 | Ductile Iron Pipe DN300 Class K9 — 6m lengths to BS EN 545 | Hargreaves Pipes Ltd | DN-2025-0041 | Pipework & Fittings | WRC-SP-003 Cl.4.2 / BS EN 545 | Test Certificate | Pass |  | J. Hargreaves | CE Declaration and Factory Test Cert checked — compliant. | Batch HPI-0441 | TCS-2025-041 |  | //server/mvt/MVT-001_cert.pdf
MVT-002 | 2025-01-21 | C40/50 Ready Mix Concrete — pump mix with 350kg OPC | Redimix Concrete Ltd | DN-2025-0089 | Concrete & Reinforcement | WRC-SP-007 / BS 8500-1 | Test Certificate | Pass |  | S. Patel | Delivery ticket checked. Slump test 80mm — within spec. | Mix 40M0003 | TCR-2025-089
MVT-003 | 2025-02-05 | HDPE Duct Pipe 110mm Ø — twinwall to BS EN 13476 | Polypipe Ltd | DN-2025-0122 | Pipework & Fittings | WRC-SP-003 Cl.5.1 | Visual | Fail | NCR-025 | T. Walsh | Wall thickness non-conforming — 3.2mm vs spec min 3.5mm. Batch quarantined. | Batch PP-9872
MVT-004 | 2025-02-19 | Epoxy Lining System — DFT 250μm to AS/NZS 4020 | Protective Coatings Ltd | DN-2025-0163 | Coatings & Linings | WRC-SP-011 Cl.6.3 | Test Certificate | Pending |  | C. Roberts | Awaiting DFT holiday test results from third party inspector. | Batch EPS-V2-44 |  | PCL-LAB-2025-163
MVT-005 | 2025-03-03 | High Yield Rebar T16 — B500B to BS 4449 | Steelco Ltd | DN-2025-0201 | Concrete & Reinforcement | BS 4449:2005 / BS 8666 | Test Certificate | Pass |  | A. Nkosi | Mill cert checked. Tensile and yield strengths compliant. | Heat STL-20251-B | TCR-2025-201 |  | //server/mvt/MVT-005_millcert.pdf
TOTAL DELIVERIES | 5 | PASS | 3 | FAIL | 1 | PENDING | 1 | NCRs RAISED | 1 | PASS RATE | 60%

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.