## Cover
EBRORA
ebrora.com
Specifications Compliance Matrix
Cross-reference CESWI / UUCESWI specification clauses against project deliverables — demonstrate clause-by-clause compliance at handover.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — Specifications Compliance Matrix
Step-by-Step Instructions
1. | Go to the 'Compliance Matrix' sheet. Enter the Project Name, Contract Number and Specification Document reference in the info strip.
2. | The matrix rows list Specification Clauses (column A = Clause Ref, column B = Clause Title, column C = brief Description). Pre-populated with common CESWI 6th Edition sections — update to match your project specification.
3. | The matrix columns (D onwards) represent Project Deliverables or compliance evidence types: Drawing Issue, Method Statement, Material Approval, ITP Closed, Test Result, O&M Submitted, and more.
4. | In each intersection cell, enter the compliance status using the dropdown: ✓ Compliant, ⚠ Partial, ✗ Non-Compliant, or N/A.
5. | The cell colour updates automatically: green for Compliant, amber for Partial, red for Non-Compliant, grey for N/A.
6. | Column D shows the overall % compliance per clause row — how many applicable evidence columns are marked Compliant.
7. | The completion row at the bottom shows % compliance per evidence column across all applicable clauses.
8. | For any ⚠ Partial or ✗ Non-Compliant cells, record the action required in the Notes column (last column).
9. | Review this matrix at each progress meeting and at pre-handover review. Every row must show 100% before the O&M pack is submitted.
10. | Print landscape for inclusion in Quality Plans, Handover Submissions, or Pre-Completion Inspection packs.
Colour Key
✓ Compliant — Clause requirement is fully satisfied by the referenced deliverable.
⚠ Partial — Clause is partially addressed. Further evidence or action required.
✗ Non-Compliant — Requirement not met. Immediate action required.
N/A — This clause does not apply to the project scope. Document the reason.
Light teal % complete column and cells — Auto-calculated. Do not edit.
Dark navy headers — Do not edit.
Tips
* | Populate this matrix at tender or contract award, not at handover. A compliance matrix completed retrospectively is an audit risk; one built progressively demonstrates genuine QMS compliance.
* | Where UUCESWI departs from CESWI, update the clause reference and description to reflect the project-specific requirement. The matrix is only as useful as it is accurate.
* | For every N/A cell, make sure there is a documented rationale — a written statement from the designer or PM confirming the clause is not applicable. Reviewers will challenge unexplained N/A entries.

## Compliance Matrix
Project Name: |  | [Enter Project Name] |  |  |  | Spec Document: |  | CESWI 6th Edition / UUCESWI
Specification Clauses |  |  |  | Project Deliverables / Compliance Evidence ¦ ✓ = Compliant ⚠ = Partial ✗ = Non-Compliant N/A = Not Applicable
Clause Ref | Clause Title | Requirement Summary | % Compliant | IFC Drawing Issued | Method Statement | Material Approval | ITP Hold Pt Closed | Test / Inspection | Pressure Test | Survey Record | O&M Submitted | O&M Approved | As-Built Drawing | Notes / Action Required
CESWI 1.1 | General Requirements | Contractor to comply with all CESWI clauses unless project-specific amendments apply. | 66.67% | ✓ Compliant | ✓ Compliant | N/A | ✓ Compliant | N/A | N/A | N/A | ✓ Compliant | ⚠ Partial | ⚠ Partial
CESWI 2.1 | Materials — General | All materials to be new, fit for purpose, and to relevant BS/EN standards. Test certs required. | 83.33% | ✓ Compliant | ✓ Compliant | ✓ Compliant | ✓ Compliant | ✓ Compliant | N/A | N/A | N/A | N/A | ⚠ Partial
CESWI 2.4 | Aggregates | Aggregates to BS EN 12620. Source approval required. Alkali-silica reactivity assessment. | —
CESWI 2.7 | Concrete | Concrete mix design to BS 8500-1. Designed mixes. Cube test regime. Durability class specified. | 85.71% | ✓ Compliant | ✓ Compliant | ✓ Compliant | ✓ Compliant | ✓ Compliant | N/A | ✓ Compliant | N/A | N/A | ⚠ Partial
CESWI 2.9 | Reinforcement | Reinforcement to BS 4449 Grade B500B. Bending schedules to BS 8666. Cover per drawing. | —
CESWI 3.1 | Earthworks — General | Formation levels, compaction testing (CBR/plate), and dewatering per specification. | —
CESWI 3.4 | Pipes — Laying & Jointing | Bedding, pipe laying, jointing and backfill per CESWI / WRc Sewers for Adoption. | 100% | ✓ Compliant | ✓ Compliant | ✓ Compliant | ✓ Compliant | ✓ Compliant | ✓ Compliant | ✓ Compliant | N/A | N/A | ✓ Compliant
CESWI 4.1 | Pipelaying — General | Pipe materials to specified standards. Cleaning and CCTV before acceptance. | —
CESWI 4.3 | Pressure Pipelines | Hydrostatic test 1.5× WP for 1 hour. ER to witness. Witnessed test record required. | 100% | ✓ Compliant | ✓ Compliant | ✓ Compliant | ✓ Compliant | ✓ Compliant | ✓ Compliant | N/A | N/A | N/A | ✓ Compliant
CESWI 5.1 | Structural Concrete | Formwork, reinforcement, pour sequence, curing, and post-pour inspection per spec. | —
CESWI 5.6 | Waterproofing | Tank lining and waterproofing per approved system. DFT checks, holiday test, WRAS compliance. | —
CESWI 6.1 | Mechanical — General | Equipment selection, installation, and commissioning per approved O&M and FAT/SAT records. | 37.5% | ✓ Compliant | ✓ Compliant | ✓ Compliant | ⚠ Partial | ⚠ Partial | N/A | N/A | ⚠ Partial | ✗ Non-Compliant | ✗ Non-Compliant | O&M not yet approved — target approval 30/04/25. As-built drawing pending designer issue.
CESWI 6.4 | Coatings | Internal coatings to specified DFT, holiday test voltage, and potable water approval. | —
CESWI 7.1 | Electrical — General | All electrical works to BS 7671:2018. EICR on completion. Safe isolation procedures. | —
CESWI 7.3 | Instrumentation | Loop testing, calibration records, and SCADA/PLC SAT per approved test procedures. | —
CESWI 8.1 | Commissioning — General | Dry and wet commissioning records. Process proving to consent limits. | —
CESWI 9.1 | Environmental | COSHH, waste management, and environmental monitoring per EMP. EA consent conditions. | —
CESWI 10.1 | Survey & Setting Out | Control network established by licensed surveyor. Check surveys every 28 days. | —
CESWI 11.1 | Health & Safety | CDM 2015 compliance. RAMS, LOTO, and LOLER records maintained and current. | —
CESWI 12.1 | Quality Management | ITP in place and maintained. NCR system active. WIS log current. QMS audit trail. | —
COLUMN COMPLIANCE % |  |  |  | 100% | 100% | 100% | 83.33% | 80% | 100% | 100% | 50% | 0% | 33.33%

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.