## Cover
EBRORA
ebrora.com
Non-Conformance Report Log
Log, track and close out non-conformance reports with root cause analysis.
Dashboard showing NCR status, severity breakdown, and average close-out time.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. | Open the 'NCR Log' sheet. The dashboard shows open/closed NCRs, severity breakdown, and average days to close.
2. | Raise an NCR for any work that doesn't meet the specification, drawing, or quality standard. Assign a unique reference.
3. | Enter the date raised, description of the non-conformance, location, severity (Critical/Major/Minor), and the discipline/trade responsible.
4. | Select the root cause category from the dropdown: Workmanship, Material, Design, Supervision, Method, or Other.
5. | Record the corrective action required and assign it to a responsible person with a target close-out date.
6. | When the corrective action is verified, enter the close-out date. Days Open auto-calculates. The status updates to Closed.
7. | Review open NCRs weekly at the quality meeting. Any NCR open >14 days should be escalated.
Colour Key
Light teal — user input
Dark navy — headers
Green — Closed / Minor severity
Amber — Major severity / corrective action in progress
Red — Critical severity / overdue / open
Tips
• | Photograph every NCR — visual evidence is essential for root cause analysis and for demonstrating corrective action.
• | Track root cause categories over time. If 'Workmanship' dominates, your briefing or supervision needs improving.
• | Close NCRs with verified evidence, not just a verbal confirmation. Re-inspect and document.

## NCR Log
NON-CONFORMANCE REPORT LOG
NCR Status |  |  |  |  | Severity Breakdown |  |  |  |  | Metrics
Open |  |  | 1 |  | Critical |  |  | 2 |  | Total NCRs: | 5
Corrective Action |  |  | 2 |  | Major |  |  | 2 |  | Close-Out Rate: | 40%
Closed |  |  | 2 |  | Minor |  |  | 1 |  | Avg Days to Close: | 14.2
NCR REGISTER
NCR Ref | Date Raised | Description | Location | Discipline | Severity | Root Cause | Corrective Action | Status | Days Open | Raised By | Target Date | Close-Out Date | Verified By
NCR-001 | 2026-02-10 | Foundation rebar cover insufficient — measured 35mm against 50mm minimum spec. | Grid A3-A5, Foundation F04 | Structural | Major | Workmanship | Strip and re-fix rebar with correct spacers. Re-inspect before pour. | Closed | 3 | M. Khan | 2026-02-14 | 2026-02-13 | T. Henderson
NCR-002 | 2026-02-18 | Concrete cube test results at 7 days below 70% of characteristic strength. | Phase 1, Pour P-012 | Structural | Critical | Material Defect | Commission independent core testing. If confirmed, structural review required. | Corrective Action | 33 | T. Henderson | 2026-02-25
NCR-003 | 2026-02-25 | Drainage pipe laid at incorrect gradient — 1:120 vs specified 1:80. | Foul drain run FD-04, MH3 to MH4 | Civil | Major | Supervision | Lift and re-lay to correct fall. Re-survey before backfill. | Closed | 6 | J. Williams | 2026-03-04 | 2026-03-03 | T. Henderson
NCR-004 | 2026-03-05 | Blockwork mortar joint thickness inconsistent — 15-20mm vs 10mm spec. | Building 2, Level 1, Elevation B | Architectural | Minor | Workmanship | Rake out and repoint affected area. Brief bricklaying gang on joint spec. | Corrective Action | 18 | M. Khan | 2026-03-12
NCR-005 | 2026-03-12 | Fire stopping missing at service penetrations through fire-rated wall. | Building 1, Riser R3, Level 2 | M&E | Critical | Supervision | Install approved fire stop system per detail FS-101. Third-party inspection required. | Open | 11 | T. Henderson | 2026-03-19
Formulas:
Days Open = IF([Date Raised]="","",IF([Status]="Closed",IF([Close-Out Date]<>"",[Close-Out Date]-[Date Raised],"Closed"),TODAY()-[Date Raised]))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.