## Cover
EBRORA
ebrora.com
Progressive Assurance Matrix
Map CQA evidence across structures and systems — demonstrate that every quality assurance activity has been completed before handover.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — Progressive Assurance Matrix
Step-by-Step Instructions
1. | Go to the 'Assurance Matrix' sheet. Enter the Project Name and Contract Number in the info strip at the top.
2. | The matrix rows (column A) list the Structures or Systems being assured — e.g. Inlet Chamber, Primary Tank, MCC Room. Add your own rows as needed.
3. | The matrix columns (row 3 onwards) represent CQA Evidence Categories — e.g. ITP Closed, Test Pack Signed, O&M Submitted. Column headers are pre-populated but can be updated to match your project's CQA plan.
4. | In each intersection cell, enter the evidence status using the dropdown: ✓ Complete, ⧖ In Progress, ✗ Outstanding, or N/A.
5. | The cell colour updates automatically: green for Complete, amber for In Progress, red for Outstanding, grey for N/A.
6. | The % Complete column (column B) calculates what percentage of applicable evidence categories are Complete for each structure/system.
7. | The completion percentage row at the bottom calculates column-by-column completion across all structures.
8. | Use the RAG Status column (column C) to set an overall readiness signal for each structure: Green, Amber, or Red.
9. | Review this matrix at fortnightly quality review meetings. Every row should be Green before that structure is submitted for handover.
10. | Print the matrix in landscape for inclusion in the Monthly Quality Report or Handover Submission Pack.
Colour Key
✓ Complete — CQA evidence item is fully closed and documented.
⧖ In Progress — Evidence is being gathered. Action underway.
✗ Outstanding — Evidence not yet started or significantly overdue.
N/A — This evidence category does not apply to this structure/system.
Dark navy column and row headers — Do not edit.
Light teal % complete cells — Auto-calculated. Do not edit.
Tips
* | Start populating this matrix early — at mobilisation, not at handover. A matrix filled in retrospectively is an audit risk; one built progressively is a quality record.
* | Align the column headers exactly with the CQA Plan sections agreed with the Employer's Representative. This makes it straightforward to demonstrate compliance during the quality audit.
* | If a cell is 'N/A', make sure there is a documented reason on file — a blank N/A without justification will be challenged during the handover review.

## Assurance Matrix
Project Name: |  | [Enter Project Name] |  |  |  |  | Contract No: |  | [Contract No]
Structure / System |  |  | CQA Evidence Categories ¦ ✓ = Complete ⧖ = In Progress ✗ = Outstanding N/A = Not Applicable
Structure / System | % Complete | RAG | ITP All Hold Points Closed | Test Packs Signed Off | Material Certs Filed | As-Built Drawings Issued | O&M Manual Submitted | O&M Manual Approved | Commissioning Record Closed | SCADA/PLC SAT Complete | Pressure / Leakage Test | Snag List Cleared | Defects Closed | CDM / H&S File Complete | Final Survey Cert Received
Inlet Works — Screen Chamber | 41.67% |  | ✓ Complete | ✓ Complete | ✓ Complete | ⧖ In Progress | ⧖ In Progress | ✗ Outstanding | ✗ Outstanding | N/A | ✓ Complete | ⧖ In Progress | ✗ Outstanding | ⧖ In Progress | ✓ Complete
Inlet Works — Grit Removal | 25% |  | ✓ Complete | ⧖ In Progress | ✓ Complete | ✗ Outstanding | ✗ Outstanding | ✗ Outstanding | ✗ Outstanding | N/A | ✓ Complete | ✗ Outstanding | ✗ Outstanding | ⧖ In Progress | ✗ Outstanding
Primary Settlement — Tank 1 | 25% |  | ✓ Complete | ✓ Complete | ✓ Complete | ✗ Outstanding | ✗ Outstanding | ✗ Outstanding | ✗ Outstanding | N/A | ⧖ In Progress | ✗ Outstanding | ✗ Outstanding | ✗ Outstanding | ✗ Outstanding
Primary Settlement — Tank 2 | —
Aeration Lane — Lane 1 | —
Aeration Lane — Lane 2 | —
Final Settlement — Tank 1 | —
Final Settlement — Tank 2 | —
MCC Room — MCC-01 | 27.27% |  | ✓ Complete | N/A | ✓ Complete | ⧖ In Progress | ⧖ In Progress | ✗ Outstanding | ⧖ In Progress | ⧖ In Progress | N/A | ✗ Outstanding | ✗ Outstanding | ⧖ In Progress | ✓ Complete
MCC Room — MCC-02 | —
SCADA / Telemetry Kiosk | —
Site Services — Foul Drainage | —
Site Services — Water Supply | —
Site Compound & Access Road | —
Blower Building | —
COLUMN COMPLETION % |  |  | 100% | 66.67% | 100% | 0% | 0% | 0% | 0% | 0% | 66.67% | 0% | 0% | 0% | 50%

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.