## Cover
EBRORA
ebrora.com
Quality Audit Checklist
Score-based quality audit with category bands, section averages, and overall audit rating.
1–5 scoring scale across documentation, workmanship, materials, H&S, and environmental.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. | Open the 'Quality Audit' sheet. Fill in the audit details (project, date, auditor) in the header form.
2. | The checklist is divided into 5 audit areas. Each area contains specific items to assess during the site visit.
3. | Score each item 1–5: 1=Non-compliant, 2=Poor, 3=Acceptable, 4=Good, 5=Excellent. Use the dropdown or type directly.
4. | Each section has an auto-calculated average score. Sections scoring below 3.0 turn red — corrective action required.
5. | The overall audit score at the top averages all section scores. Record any observations and required actions in the notes column.
6. | Scores 1–2 trigger a mandatory corrective action. Record these in the Actions Required section at the bottom.
7. | File the completed audit in the quality management system. Schedule follow-up audits for any section scoring below 3.5.
Colour Key
Light teal — user input (score + notes)
Dark navy — section headers
Green — score 4–5 (Good/Excellent)
Amber — score 3 (Acceptable — room for improvement)
Red — score 1–2 (Non-compliant/Poor — action required)
Tips
• | Audit unannounced where possible — this gives a true picture of daily quality performance.
• | Photograph examples of both good and poor practice. Use photos in the next toolbox talk for maximum impact.
• | Trend your audit scores over time. Improving scores demonstrate your quality management system is effective.

## Quality Audit
QUALITY AUDIT CHECKLIST
Project: | Example Infrastructure Project
Date: | 2026-03-20 | Auditor: | T. Henderson
SCORING: 1=Non-compliant 2=Poor 3=Acceptable 4=Good 5=Excellent
OVERALL AUDIT SCORE: |  | 4.18
DOCUMENTATION & RECORDS |  |  | 4.5
# | Audit Item | Score | Notes / Observations
1 | Method statements available and current for all active works | 5
2 | Risk assessments in place and communicated to workforce | 4
3 | Permits to work issued where required (hot works, confined space, etc.) | 5 | Risk assessment for excavation needs updating — raised as action.
4 | Inspection records up to date (ITP sign-offs, hold points) | 4
5 | Drawing register current — latest revisions on site | 4
6 | Quality records filed and accessible (test certs, delivery notes) | 5
WORKMANSHIP & STANDARDS |  |  | 4
# | Audit Item | Score | Notes / Observations
1 | Work executed in accordance with approved drawings and specifications | 4
2 | Setting out accuracy within tolerances | 4 | Minor tolerance issue at Grid C — within spec but flagged for monitoring.
3 | Finishes and appearance meet expected standard | 3
4 | Protection of completed works in place and effective | 4
5 | Temporary works designed, checked, and installed correctly | 5
MATERIALS & STORAGE |  |  | 4
# | Audit Item | Score | Notes / Observations
1 | Materials match specification and approved products list | 4
2 | Material test certificates and delivery tickets on file | 5 | Aggregate storage area needs tidying. Cover sheets torn on 2 stockpiles.
3 | Storage areas clean, organised, and materials protected from weather | 3
4 | Batch numbers / traceability maintained for critical materials | 4
5 | Waste materials segregated and stored in designated areas | 4
HEALTH & SAFETY COMPLIANCE |  |  | 4.4
# | Audit Item | Score | Notes / Observations
1 | PPE worn correctly by all personnel observed | 5
2 | Housekeeping — work areas tidy, access routes clear | 4 | Good housekeeping overall. One access route partially blocked — cleared during audit.
3 | Scaffolding / edge protection inspected and tagged | 4
4 | Plant and equipment pre-use checks completed | 5
5 | Welfare facilities clean and stocked | 4
ENVIRONMENTAL COMPLIANCE |  |  | 4
# | Audit Item | Score | Notes / Observations
1 | Silt and sediment controls in place and effective | 4
2 | Dust and noise suppression measures active | 3 | Haul road dust visible. Water bowser requested for afternoon shift.
3 | Waste management — correct segregation and disposal | 4
4 | Spill kits accessible and fully stocked | 5
5 | Ecological exclusion zones maintained | 4
CORRECTIVE ACTIONS REQUIRED
# | Action | Owner | Due Date
1 | Update excavation risk assessment to reflect current works — reissue to workforce. | M. Khan | 25/03/2026
2 | Repair/replace torn cover sheets on aggregate stockpiles. | J. Williams | 22/03/2026
3 | Deploy water bowser to haul road during dry conditions — add to daily briefing. | A. Hussain | 21/03/2026
Auditor Signature:

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.