## Cover
EBRORA
ebrora.com
Snagging / Defects List
Track, manage and close out snagging items and defects through to practical completion — with priority tracking, category breakdown, and overdue alerts.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Defects List' sheet. The top section shows a live dashboard with status counts, priority breakdown, and completion percentage.
2. | Each row in the main log below represents one snagging or defect item. Fill in the light teal cells.
3. | Enter an Item Number, Date Raised, the Location (room, zone, or grid ref), and a clear Description of the defect.
4. | Select a Category from the dropdown (Architectural, M&E, Structural, Finishes, External, Services) and set the Priority (High, Medium, Low).
5. | Set the Status: Open, In Progress, Resolved, or Disputed. Assign the item to a person and set a Target Date for resolution.
6. | The 'Days Overdue' column calculates automatically — it shows how many days past the target date an unresolved item is. Zero or blank means it's not yet overdue.
7. | Expand the optional columns (click [+]) to record subcontractor, estimated cost to rectify, photo references, resolution date, and sign-off details.
8. | The dashboard updates in real time as you add and resolve items.
Colour Key
Light teal cells (#E8F6F7) — Editable input cells.
Dark navy headers (#1B2A4A) — Do not edit.
Green — Status is 'Resolved' or Priority is 'Low'.
Amber — Status is 'In Progress' or Priority is 'Medium'.
Red — Status is 'Open' / 'Disputed', Priority is 'High', or item is overdue.
Tips
Tip 1: | Walk the site with this list on a tablet. Log items in real time with location and photo references — it's far more reliable than writing notes and typing them up later.
Tip 2: | Filter by Status = 'Open' and sort by Priority = 'High' before your weekly subcontractor coordination meeting. This gives you a focused punch list.
Tip 3: | Don't close items without physical verification. Use the 'Verified By' optional column to record who checked the fix on site.

## Defects List
SNAGGING / DEFECTS LIST
STATUS OVERVIEW
Total Items |  | Open |  | In Progress |  | Resolved |  | Disputed |  | % Complete
5 |  | 1 |  | 1 |  | 2 |  | 1 |  | 40%
PRIORITY BREAKDOWN
High (Open) |  |  | Medium (Open) |  |  | Low (Open) |  |  | Overdue Items
2 |  |  | 1 |  |  | 0 |  |  | 3
BY CATEGORY (OPEN)
Architectural |  | M&E |  | Structural |  | Finishes |  | External |  | Services
1 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0
▸ Optional Fields — Click [+] to expand
Item No. | Date Raised | Location | Description | Category | Priority | Status | Assigned To | Target Date | Date Resolved | Days Overdue | Subcontractor | Est. Cost (£) | Photo Ref | Verified By | Sign-Off Date
1 | 2026-02-10 | Block A - Flat 12 - Bathroom | Cracked wall tile behind WC — visible hairline crack running 150mm vertically | Finishes | Medium | In Progress | J. Wilson (Apex Tiling) | 2026-03-10 |  | 12 | Apex Tiling Ltd | 85 | IMG_0412.jpg
2 | 2026-02-10 | Block A - Flat 14 - Kitchen | Worktop not level — 5mm fall over 600mm run. Does not meet tolerance. | Architectural | High | Open | D. Khan (Interiors Ltd) | 2026-03-01 |  | 21 | Interiors Ltd | 320 | IMG_0415.jpg
3 | 2026-02-12 | Block B - Corridor L1 | Fire door closer not engaging — door stays open past 15 degrees | M&E | High | Resolved | T. Brennan (FireSafe) | 2026-02-28 | 2026-02-25 |  | FireSafe Installations | 0 | IMG_0430.jpg | S. Patel | 2026-02-26
4 | 2026-02-15 | Block A - Stairwell 2 | Handrail bracket loose at mid-landing — wobbles under load | Structural | High | Disputed | R. Okonkwo (SteelFix) | 2026-03-05 |  | 17 | SteelFix Metalwork | 150 | IMG_0445.jpg
5 | 2026-02-18 | External - Car Park | Line marking paint faded on 3 disabled bays — not to BS 8300 standard | External | Low | Resolved | M. Briggs (Groundworks) | 2026-03-15 | 2026-03-08 |  | Briggs Groundworks | 200 | IMG_0460.jpg | A. Hughes | 2026-03-09
Formulas:
Services = IF(AND([Disputed]<>"",[Resolved]<>"Resolved",[Resolved]<>"",TODAY()>[Disputed]),TODAY()-[Disputed],"")

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.