## Cover
EBRORA
ebrora.com
Daily Progress Report
A structured daily site report covering labour, plant, progress, issues, and forward planning — designed to be completed in under 10 minutes at the end of each shift.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Daily Report' sheet. This is a single-page form — fill it in once at the end of each day or shift.
2. | Complete the header: Date, Report No., Weather, Temperature, Wind, Shift Start/End times. These set the context for the day.
3. | In the Labour Summary mini-table, enter the headcount and hours worked for each trade on site that day. Total headcount and man-hours calculate automatically.
4. | List key plant and equipment on site in the Plant section. Use the dropdown for status (Working/Idle/Breakdown/Off-Hired).
5. | Write a brief narrative of the day's key activities, any issues or delays encountered, and tomorrow's planned activities in the text areas.
6. | Complete the sign-off section at the bottom with your name and the date. Print or save as PDF for your daily records file.
7. | To use this for a new day: Save a copy (File > Save As) with the date in the filename, e.g. 'Daily Report 2026-03-23.xlsx'. Keep a folder of daily reports.
Colour Key
Light teal cells — Editable input cells. Fill these in.
Teal section headers — Section dividers. Do not edit.
Dark navy header — Report title. Do not edit.
Green — Plant status 'Working'.
Amber — Plant status 'Idle'.
Red — Plant status 'Breakdown'.
Tips
Tip 1: | Complete this at the end of each shift while everything is fresh. A 5-minute report written the same day is worth more than a detailed one written three days later from memory.
Tip 2: | Be specific in the narrative sections. Instead of 'Concrete poured', write 'Concrete pour to GB-12 — 18m³, Hanson, ticket HC-440355, pump started 08:30, completed 11:15.'
Tip 3: | Cross-reference issues with your Risk Register and Weather Delay Log. If something went wrong today, make sure it's captured in the right place for contractual records.

## Daily Report
DAILY PROGRESS REPORT
Project Name: | Riverside Gateway Phase 2 | Date: | 2026-03-22 | Report No.: | DPR-087
Site Manager: | S. Patel | Weather: | Overcast, light rain AM | Temp (°C): | 9
Shift Start: | 7:00 | Shift End: | 17:30 | Wind: | Light, <15mph
Overall Status: | On Track | Safety Incidents: | None | Visitors: | 2 (see visitor log)
1. LABOUR SUMMARY
Trade | Company | Headcount | Hours | Area / Activity | Notes
Groundworks | Briggs GW | 6 | 63 | Pad founds PF-07 to PF-09
Concrete | McAlpine (directs) | 4 | 42 | Ground beams GB-10/11 | Pour completed 11:15
Steelwork | SteelFix | 6 | 63 | L2 frame Zone A erection | 2 columns behind — see Issues
M&E | Northern M&E | 3 | 31.5 | L1 riser containment
Scaffolding | ScaffCo | 4 | 42 | Block B south elevation | Completed to L3
Cleaning | CleanSite Ltd | 2 | 16 | Welfare & access roads
TOTAL |  | 25 | 257.5
2. PLANT ON SITE
Item | Type / Description | Operator | Status | Hours Used | Notes
P-01 | 20t Tracked Excavator (CAT 320) | M. Briggs | Working | 8.5
P-02 | Tower Crane (Liebherr 172EC) | K. Davies | Working | 9
P-03 | Concrete Boom Pump | Supplier op. | Working | 3.5 | AM only — off-site by 12:00
P-04 | 6t Forward Tip Dumper | Agency | Idle | 0 | Stood down — no muck away today
P-05 | Telehandler (JCB 540) | R. Evans | Working | 7 | Steel offloading + distribution
3. KEY ACTIVITIES COMPLETED TODAY
• Concrete pour to ground beams GB-10 and GB-11 completed. 18m³ from Hanson (ticket HC-440390). Pump started 08:30, pour complete 11:15. Cube samples taken (CUB-010A/B/C). • Steel erection continued on Level 2 Zone A — 4 of 6 columns erected. 2 remaining columns delayed (see Issues). • Scaffold to Block B south elevation completed to Level 3. Inspection booked for tomorrow AM. • M&E first fix containment progressing in Level 1 risers — approx 60% complete.
4. ISSUES, DELAYS & RISKS
• Steel erection: 2 columns for Zone A arrived with incorrect connection detail. SteelFix have raised RFI-042 with the SE. Columns set aside, work re-sequenced to Zone B connections tomorrow. Potential 2-day delay to Zone A frame if not resolved by Wednesday. • Light rain 06:00–09:30 — no impact on programme (covered works only this AM). Logged in Weather Delay Log as 'Minor'.
5. TOMORROW’S PLANNED ACTIVITIES
• Excavation for pad foundations PF-10 to PF-12 (Briggs GW). • Steel erection — Zone B connections and bracing (SteelFix). Zone A on hold pending RFI response. • Scaffold inspection Block B south (ScaffCo + site team). • M&E containment continue L1 risers — target 80% by end of day.
6. SIGN-OFF
Prepared By: | S. Patel — Site Manager | Date: | 2026-03-22 | Signature:
Reviewed By: |  | Date: |  | Signature:
ebrora.com — Free professional construction management templates

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.