## Cover
EBRORA
ebrora.com
Daily Site Diary
Record daily site activities, workforce numbers, weather conditions, deliveries, delays, and health & safety observations in one structured log.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Navigate to the 'Daily Site Diary' sheet tab to begin logging daily records.
2. | Each row represents one day's diary entry. Fill in one row per working day.
3. | Start by entering the date and selecting the weather conditions from the dropdown list.
4. | Record the total workforce and contractor numbers on site for the day.
5. | Use the 'Key Activities / Works Carried Out' column to summarise the main works undertaken — keep it factual and concise.
6. | Log any visitors, deliveries, and plant/equipment present on site.
7. | Record any health & safety issues or observations in the dedicated column.
8. | If there were delays or disruptions, select the delay type from the dropdown and enter the number of hours lost.
9. | Set the status for each entry: Complete, In Progress, or Carried Over.
10. | Use the summary section at the top of the data sheet to review key metrics at a glance.
Colour Key
Light teal cells (#E8F6F7) — These are editable input cells. Enter your data here.
Dark navy header row — Column headings. Do not edit.
Green fill — Status is 'Complete' or no issues flagged.
Amber fill — Status is 'In Progress' or minor concern.
Red fill — Status is 'Carried Over', delays logged, or H&S issue flagged.
Tips
Complete the diary at the end of each working day while details are fresh — don't leave it until the end of the week.
Be specific in the 'Key Activities' column: reference grid lines, bay numbers, levels, or areas of the site to make entries traceable.
Use the 'Additional Notes' column to record anything unusual — client instructions, design changes, or verbal agreements that need following up.

## Daily Site Diary
DAILY SITE DIARY |  |  | Total Entries: | 100 |  | Total Delay Hours: | 6 |  | Days with Delays: | 2 |  | Avg Workforce/Day: | 36
No. | Date | Weather | Temp (°C) | Site Manager on Duty | Total Workforce | Contractors on Site | Key Activities / Works Carried Out | Visitors to Site | Deliveries Received | Plant / Equipment on Site | H&S Issues / Observations | Delay Type | Delay Hours | Status | Additional Notes / Comments
1 | 2026-03-16 | Overcast | 8 | James Thornton | 34 | 12 | Earthworks underway in Zone A — bulk excavation to formation level. Piling rig mobilised for Phase 2. | HSE Advisor — routine walkdown | 50m³ ready-mix concrete (Hanson) | 2× JCB 3CX, 1× CAT 320 excavator, 1× Liebherr LTM 1060 crane |  | None | 0 | Complete
2 | 2026-03-17 | Light Rain | 6 | Sarah Jennings | 41 | 18 | Concrete pour to Bay 3 ground-floor slab (48m³). Rebar fixing ongoing in Bay 4. Drainage run to MH7 completed. |  | Rebar delivery (BRC) | 2× concrete pumps, 1× CAT 320, poker vibrators | Near miss — unsecured load on delivery vehicle. Toolbox talk issued. | None | 0 | Complete | Near miss ref NM-026-003 raised and closed same day.
3 | 2026-03-18 | Heavy Rain | 4 | James Thornton | 22 | 8 | Reduced operations due to heavy rainfall. Internal works continued on Block B fit-out. Standing water pumped from excavation. | Client PM — John Davies |  | Dewatering pump, 1× JCB 3CX | Standing water in excavation — pump deployed. No incidents. | Weather | 4 | In Progress | External works suspended from 11:00. Weather forecast reviewed — expected to clear overnight.
4 | 2026-03-19 | Sunny | 11 | Sarah Jennings | 45 | 20 | Full operations resumed. Steelwork erection to Block A Level 2. Brickwork commenced on Block C ground floor. Drainage to MH8–MH10. | Building Control — slab inspection (passed) | Structural steel (Severfield), facing brick (Ibstock) | 1× Liebherr LTM 1060, 2× MEWPs, 1× JCB Telehandler |  | None | 0 | Complete | Building Control confirmed ground-floor slab passed inspection.
5 | 2026-03-20 | Overcast | 9 | James Thornton | 38 | 15 | Steelwork erection continued — Level 2 beams and columns complete. M&E first fix rough-in commenced Block B. Subcontractor Apex Electrical mobilised. | Apex Electrical — site induction | M&E containment and cable tray (CEF) | 1× Liebherr LTM 1060, 2× MEWPs, scaffolding crew |  | Material | 2 | Carried Over | Delayed delivery of cable tray — Apex Electrical start pushed to PM only. Procurement chasing supplier.

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.