## Cover
EBRORA
ebrora.com
Night Shift Handover Log
A structured shift handover form ensuring safe, clear communication between outgoing and incoming crews — with live hazard tracking and dual sign-off.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Handover Log' sheet. This is a single-page form split into two panels: the left side is for the Outgoing Shift, the right side for the Incoming Shift.
2. | The outgoing shift supervisor fills in the left panel at the end of their shift: what was completed, any issues, and what's outstanding.
3. | The incoming shift supervisor reads the left panel, then fills in the right panel: acknowledging the handover, confirming their plan, and noting any concerns.
4. | The Live Hazards & Permits section in the middle lists active permits, isolations, and known hazards that carry over between shifts. Both parties must review this together.
5. | Both supervisors sign off at the bottom. The handover is not complete until both signatures are present.
6. | Print or save a copy for each shift change. File in chronological order in your site records.
Colour Key
Light teal cells (left panel) — Outgoing shift input.
Warm-tinted cells (right panel) — Incoming shift input.
Teal section headers — Section dividers.
Red in hazard status — Active / unresolved hazard.
Green in hazard status — Controlled / cleared.
Amber in hazard status — Monitoring required.
Tips
Tip 1: | Do the handover face-to-face, walking the site together. Use this form as a structured agenda — it ensures nothing gets missed in a verbal-only handover.
Tip 2: | Never leave the Live Hazards section blank. If there are genuinely no active permits or hazards, write 'NONE' — this confirms it was checked, not overlooked.
Tip 3: | Keep a copy of every night shift handover. In the event of an incident investigation, these forms are primary evidence of what information was communicated and when.

## Handover Log
NIGHT SHIFT HANDOVER LOG
Project: | Riverside Gateway Phase 2 |  |  | Date: | 2026-03-22 | Report No.: | NSH-041
Day Shift End: | 17:30 | Night Shift Start: | 18:00 | Night Shift End: | 6:00 | Weather: | Clear, dry, 4°C
Day Supervisor: | S. Patel | Day Headcount: | 25 | Night Supervisor: | R. Okonkwo | Night Headcount: | 12
◀ OUTGOING SHIFT (completed by day supervisor) |  |  |  | INCOMING SHIFT (completed by night supervisor) ▶
WORK COMPLETED TODAY |  |  |  | TONIGHT’S PLANNED ACTIVITIES
• Concrete pour to ground beams GB-12/13 completed (24m³, Hanson) • Steel erection L2 Zone A — 6 of 6 columns complete • M&E riser containment L1 — 100% complete • External drainage run DR-04 to DR-06 laid and tested |  |  |  | • Concrete pour — lift core base slab LC-01 (42m³, Cemex, pump booked 20:00) • Steel bolting torque checks L2 Zone A (must complete before L3 erection) • Waterproofing 2nd coat to lift pit LC-01 (after pour cures)
OUTSTANDING / INCOMPLETE |  |  |  | CONCERNS / QUERIES FOR OUTGOING SHIFT
• Scaffold inspection Block B south — deferred to tomorrow AM (ScaffCo left early) • Waterproofing to lift pit LC-01 — 2nd coat needed, material on site |  |  |  | • Confirmed pump access route for tonight — via south gate, reversing bay clear? • Is the tower crane available from 20:00 or still under day shift use until 21:00?
ISSUES / INCIDENTS |  |  |  | HANDOVER ACKNOWLEDGED
• Near miss reported 14:30 — unsecured panel blew off hoarding in wind gust. Logged as NM-026. Area secured with additional fixings. • No injuries, no damage. Hoarding inspection added to morning checks. |  |  |  | • Outstanding items noted — scaffold inspection will be raised with ScaffCo AM. • Near miss NM-026 reviewed. Hoarding check added to tonight’s patrol route. • All live permits and isolations reviewed and understood.
⚠ LIVE HAZARDS, PERMITS & ISOLATIONS (both parties must review)
No. | Description | Type | Location | Permit/Ref | Status | Action Required | Owner
1 | Excavation open — pad foundation PF-10, 2.5m deep | Excavation | Grid A4-A5 | PTW-089 | Active | Barriers and lighting in place. No entry without banksman. | S. Patel
2 | Electrical isolation — DB-L1-03 locked off for M&E works | Isolation | Level 1 riser | ISO-034 | Active | LOTO applied. Key held by T. Brennan (day) / R. Okonkwo (night). | T. Brennan
3 | Tower crane radius over public footpath (south) | Crane Lift | South boundary | PTW-091 | Controlled | Banksman stationed. Out-of-hours lifts permitted under PTW. | K. Davies
4 | Loose hoarding panel section 4 (near miss NM-026) | Hazardous Area | West boundary | NM-026 | Monitoring | Temporary fixings applied. Permanent fix scheduled tomorrow. | S. Patel
SIGN-OFF
Outgoing Supervisor: | S. Patel |  | Signature: | Incoming Supervisor: | R. Okonkwo |  | Signature:
Date: | 2026-03-22 | Time: | 17:45 | Date: | 2026-03-22 | Time: | 18:00
ebrora.com — Free professional construction management templates

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.