## Cover
EBRORA
ebrora.com
Agency Labour Tracker
Track agency workers, daily hours, charge rates, and weekly costs against budget.
Dashboard showing agency spend, headcount, and budget variance for construction projects.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. | Open the 'Agency Tracker' sheet. Set your weekly agency budget in the header. The dashboard tracks spend vs budget.
2. | Log each agency worker in the main table. Enter their name, agency, trade, start date, day rate, and weekly hours worked.
3. | The Weekly Cost column auto-calculates (hours × hourly equivalent, or use day rate × days — adjust the formula to your arrangement).
4. | The Cumulative Spend column keeps a running total. Budget variance auto-calculates and turns red if overspent.
5. | Use the Status column to track whether each worker is Active, Stood Down, or Finished.
6. | Expand optional columns for agency reference, PO number, CSCS verified, induction date, and performance notes.
7. | Review weekly with your commercial manager. Agency labour is typically the fastest-growing uncontrolled cost on site.
Colour Key
Light teal — user input / editable
Dark navy — headers
Green — Active / under budget
Amber — approaching budget (>80%)
Red — over budget / finished worker still on register
Tips
• | Always check agency workers have valid CSCS cards and site inductions before they start. Record in the optional columns.
• | Negotiate capped day rates with agencies upfront. Overtime should be pre-authorised, not discovered on the invoice.
• | If an agency worker is on site for >12 weeks, AWR (Agency Workers Regulations) gives them equal pay and conditions.

## Agency Tracker
AGENCY LABOUR TRACKER
Weekly Budget: |  | 8000 |  | Dashboard |  |  |  | Budget Status
|  |  |  | Active Workers: | 4 | Total This Week: | 3740 | Spend This Period: | 0 | Variance:
[8 empty] | Budget: | 8000 | 8000
AGENCY WORKER LOG
Name | Agency | Trade | Start Date | Day Rate (£) | Days This Week | Weekly Cost (£) | Status | Agency Ref | PO Number | CSCS Verified | Induction Date | Weeks on Site | Notes
R. Nowak | StaffLine Construction | Labourer | 2026-01-15 | 185 | 5 | 925 | Active | SL-20260115-A | PO-2026-041 | Yes | 2026-01-15 |  | Reliable. Extended for Phase 2.
K. Patel | BuildForce Ltd | Banksman | 2026-02-03 | 195 | 5 | 975 | Active | BF-20260203-B | PO-2026-042 | Yes | 2026-02-03 |  | Crane lifting phase
T. Kowalski | StaffLine Construction | Labourer | 2026-02-17 | 185 | 4 | 740 | Active | SL-20260217-C | PO-2026-041 | Yes | 2026-02-17
J. Mensah | Randstad Construction | Steel Fixer | 2026-03-01 | 220 | 5 | 1100 | Active | RS-20260301-D | PO-2026-055 | Yes | 2026-03-01 |  | Specialist rebar — RC frame
L. Silva | BuildForce Ltd | Labourer | 2025-11-10 | 185 | 0 | 0 | Stood Down | BF-20251110-E | PO-2026-038 | Yes | 2025-11-10 |  | Stood down — awaiting next phase
Formulas:
Weeks on Site = IF([Start Date]="","",INT((TODAY()-[Start Date])/7))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.