## Cover
EBRORA
ebrora.com
Daily Labour Allocation Sheet
Track daily workforce deployment by trade, subcontractor, and work area — with auto-calculated totals, shift tracking, and labour summaries.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Go to the “Labour Allocation Sheet” tab. Each row records one trade/subcontractor deployment for one day.
2. | Enter the Date and select the Trade/Discipline from the dropdown (e.g. General Labour, Groundworks, Steel Fixing, M&E, etc.).
3. | Enter the Subcontractor/Company name and the number of Operatives and Supervisors deployed.
4. | The Total on Site column auto-calculates (Operatives + Supervisors) for each row.
5. | Record the Work Area/Location and a brief Activity Description.
6. | Enter the name of the person recording the allocation in “Recorded By”.
7. | Expand optional columns for: Shift type (Day/Night/Split), Start Time, Finish Time, Hours Worked (auto-calculated), and Notes.
8. | The dashboard auto-calculates total workforce, total operatives, total supervisors, unique trades active, unique subcontractors, and average team size.
9. | Use one row per trade per subcontractor per day. If a subcontractor has operatives in two different areas, use two rows.
Colour Key
• | Light teal cells = User input / editable fields.
• | Dark navy headers = Column headers. Do not edit.
• | White cells with formulas = Auto-calculated — do not overwrite.
• | Grey row shading = Weekend date (Saturday or Sunday).
• | Amber highlight on Total = 10 or more people in one entry (large gang — may need additional supervision).
Tips
• | Fill this in every morning during the pre-start briefing. It takes 5 minutes and gives you a complete picture of who’s on site, where they are, and what they’re doing.
• | The data feeds directly into your daily progress report and weekly labour returns. Keep it accurate and your reporting writes itself.
• | Filter by Subcontractor to see their total headcount, or by Trade to check resource levels against your look-ahead programme.

## Labour Allocation Sheet
DAILY LABOUR ALLOCATION SHEET |  |  |  | Total Workforce: | 51 |  | Total Operatives: | 40
|  |  |  | Total Supervisors: | 11 |  | Total Entries: | 7
|  |  |  | Unique Trades Active: | 7 |  | Avg Team Size: | 7.2857
|  |  |  | Largest Single Entry: | 14 |  | Total Hours: | 64.5
▸ Optional Fields — Click [+] to expand
Entry No. | Date | Trade / Discipline | Subcontractor / Company | No. Operatives | No. Supervisors | Total on Site | Work Area / Location | Activity Description | Recorded By | Shift | Start Time | Finish Time | Hours Worked | Notes
1 | 2026-03-16 | Groundworks | Civils Direct Ltd | 8 | 1 | 9 | Block C, Piling Mat & Drainage | Drainage run DR-03 excavation and pipe laying. Piling mat preparation. | M. Davies | Day | 7:30 | 17:00 | 9.5
2 | 2026-03-16 | Steel Fixing | ProSteel Ltd | 6 | 1 | 7 | Block A, Ground Floor | Rebar fixing to ground beams GB-12 to GB-18. | M. Davies | Day | 7:30 | 17:00 | 9.5
3 | 2026-03-16 | M&E Electrical | MechServ Ltd | 4 | 1 | 5 | Block B, Ground Floor | First fix containment and cable tray installation. | M. Davies | Day | 8:00 | 17:00 | 9
4 | 2026-03-16 | Concrete | ReadyMix Contracts Ltd | 6 | 1 | 7 | Block A, Ground Floor | Concrete pour to pad foundations PF-01 to PF-04. 40m³ C32/40. | M. Davies | Day | 7:00 | 15:00 | 8
5 | 2026-03-16 | Brickwork/Blockwork | Mason Brothers Ltd | 12 | 2 | 14 | Block A, North Elevation | Brickwork courses 1–12, north elevation. Scaffold access. | M. Davies | Day | 7:30 | 17:00 | 9.5
6 | 2026-03-16 | Scaffolding | Apex Scaffolding Ltd | 4 | 1 | 5 | Block A, North Elevation | Scaffold lift to level 2. Additional bay erected for brickwork access. | M. Davies | Day | 7:30 | 16:00 | 8.5
7 | 2026-03-16 | Management/Supervision | Main Contractor | 0 | 4 | 4 | Site-wide | Site manager, assistant SM, site engineer, HSE advisor. | M. Davies | Day | 7:00 | 17:30 | 10.5

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.