Red-Line Markup Procedure

| Document Ref: | Enter reference | Revision: | Enter revision |
| --- | --- | --- | --- |
| Project Name: | Enter project name | Contract No: | Enter contract number |
| Date: | DD / MM / YYYY | Prepared By: | Name and role |
| Approved By: | Name and role | Client: | Enter client name |

# 1. Purpose

This procedure defines the requirements for maintaining red-line markup drawings on site throughout the construction phase. Red-line markups capture all deviations from the construction issue drawings and form the basis for the production of final as-built records at project completion. Amend this section to reflect project-specific requirements. Delete guidance text before issuing.

# 2. Scope

This procedure applies to all construction drawings used on site, including but not limited to: architectural, structural, civil, mechanical, electrical, instrumentation, piping, landscaping, and external works drawings. It applies to all principal contractor staff, subcontractors, and specialist installers working on the project.

# 3. Definitions

| Red-Line Markup: | A physical annotation made on a printed construction issue drawing using a red pen to record any deviation from the designed or specified arrangement. |
| --- | --- |
| As-Built Drawing: | A final drawing produced by incorporating all red-line markups into the original CAD or BIM file, representing the works as actually constructed. |
| Construction Issue Drawing: | The latest approved revision of a drawing issued for construction purposes. |
| Deviation: | Any change from the construction issue drawing, including dimensional changes, route changes, material substitutions, additional works, or omitted works. |

# 4. Responsibilities

| Role | Responsibility |
| --- | --- |
| Site Manager / Project Manager | Overall responsibility for ensuring red-line markups are maintained and submitted on time. |
| Section Engineer | Day-to-day management of red-line markups within their section. Responsible for checking accuracy and completeness. |
| Setting Out Engineer | Recording dimensional changes, positional deviations, and level changes on red-line drawings. |
| Subcontractor Foreman | Responsible for marking up all deviations within their scope of works and submitting to the section engineer. |
| M&E Coordinator | Responsible for coordinating MEP red-line markups from all services subcontractors. |
| Document Controller | Maintaining the red-line markup register and tracking submission status. |
| Design Team / CAD Technician | Incorporating red-line markups into final as-built drawings. |

# 5. Red-Line Markup Requirements

## 5.1 General Rules

- All markups must be made using a red pen (fine tip, permanent ink) on a clean, current-issue print of the construction drawing.

- Markups must be clear, legible, and unambiguous. Use standard drawing conventions and symbols.

- Every markup must include the date of the change and the initials of the person making the markup.

- Where dimensions have changed, cross through the original dimension in red and write the as-built dimension alongside.

- Where items have been omitted, strike through in red and annotate 'OMITTED' with date and initials.

- Where items have been added, draw in red and annotate 'ADDED' with date, initials, and relevant RFI or SI reference.

- Where routes, levels, or positions have changed, mark the as-built position in red and annotate with actual dimensions or co-ordinates.

- Reference the relevant site instruction (SI), request for information (RFI), variation order, or NCR number alongside every change.

## 5.2 Information to Record

| No. | Item to Record on Red-Line Markup |
| --- | --- |
| 1 | Changes to horizontal or vertical alignment of any element |
| 2 | Changes to pipe, duct, or cable routes from designed positions |
| 3 | Actual invert levels, cover levels, and depths of buried services |
| 4 | Positions of manholes, chambers, and access points as built |
| 5 | Location and depth of all underground services and utilities |
| 6 | Material substitutions or specification changes |
| 7 | Structural modifications, additional reinforcement, or design changes |
| 8 | Positions of expansion joints, movement joints, and waterstops |
| 9 | Actual positions of piles, foundations, and structural connections |
| 10 | Changes to room layouts, partition positions, or door locations |
| 11 | Changes to MEP equipment positions, sizes, or specifications |
| 12 | Fire stopping and compartmentation details where deviated from design |
| 13 | Any temporary works left in place permanently |
| 14 | Positions of monitoring instruments, survey markers, or reference points |

# 6. Submission and Review Process

| Submission Frequency: | e.g. Monthly, at each section completion, at practical completion |
| --- | --- |
| Submitted To: | Name and role of person receiving red-line markups |
| Review Period: | e.g. 5 working days from submission |
| Final As-Built Deadline: | e.g. Within 28 days of practical completion |
| Storage Location: | Describe where physical red-line drawings are stored on site |

# 7. Red-Line Markup Register

| No. | Drawing Number | Drawing Title | Discipline | Marked Up By | Date Submitted | Status | As-Built Issued? |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  | DD/MM/YY |  | Y / N |
| 2 |  |  |  |  | DD/MM/YY |  | Y / N |
| 3 |  |  |  |  | DD/MM/YY |  | Y / N |
| 4 |  |  |  |  | DD/MM/YY |  | Y / N |
| 5 |  |  |  |  | DD/MM/YY |  | Y / N |
| 6 |  |  |  |  | DD/MM/YY |  | Y / N |
| 7 |  |  |  |  | DD/MM/YY |  | Y / N |
| 8 |  |  |  |  | DD/MM/YY |  | Y / N |
| 9 |  |  |  |  | DD/MM/YY |  | Y / N |
| 10 |  |  |  |  | DD/MM/YY |  | Y / N |

# 8. Approval and Distribution

| Recipient | Date Issued |
| --- | --- |
| Site Management Team | DD/MM/YYYY |
| Section Engineers | DD/MM/YYYY |
| Subcontractor Supervisors | DD/MM/YYYY |
| M&E Coordinator | DD/MM/YYYY |
| Document Controller | DD/MM/YYYY |
| Design Team | DD/MM/YYYY |
| Client / Contract Administrator | DD/MM/YYYY |

# 9. Sign-Off

| Prepared By: | Name | Signature: |  |
| --- | --- | --- | --- |
| Position / Role: | Enter role | Date: | DD / MM / YYYY |
| Approved By: | Name | Signature: |  |
| Position / Role: | Enter role | Date: | DD / MM / YYYY |

# 10. Document Control

| Revision | Date | Description of Change | Author | Approved By |
| --- | --- | --- | --- | --- |
| 01 | DD/MM/YYYY | Initial issue |  |  |
|  | DD/MM/YYYY |  |  |  |
|  | DD/MM/YYYY |  |  |  |