Process Start-Up Checklist

| Document Ref: | Enter reference | Revision: | Enter revision |
| --- | --- | --- | --- |
| Project Name: | Enter project name | Contract No: | Enter contract number |
| Date: | DD / MM / YYYY | Prepared By: | Name and role |
| Approved By: | Name and role | Start-Up Authorised By: | Name and role |

# 1. System / Process Identification

| System / Process Name: | e.g. Primary settlement, aeration, chemical dosing, pumping station |
| --- | --- |
| System Tag / Reference: | Enter system tag number |
| P&ID Reference(s): | List all relevant P&ID drawing numbers |
| GA Drawing Reference: | Enter general arrangement drawing reference |
| Location / Area: | Enter building or area on site |
| Design Capacity / Duty: | e.g. Flow: l/s, Pressure: bar, Power: kW |
| Process Medium: | e.g. Raw water, settled sewage, return activated sludge, chemical |

# 2. Pre-Start-Up Prerequisites

| No. | Prerequisite | Yes | No | N/A | Initials |
| --- | --- | --- | --- | --- | --- |
| 1 | All construction works for this system complete and signed off |  |  |  |  |
| 2 | Punch list / snagging items cleared or assessed as non-critical for start-up |  |  |  |  |
| 3 | All mechanical installation records complete and signed off |  |  |  |  |
| 4 | All electrical installation records and test certificates complete |  |  |  |  |
| 5 | All ICA (instrumentation) loop checks complete and signed off |  |  |  |  |
| 6 | Pressure / leak tests completed and certificates available |  |  |  |  |
| 7 | Chemical cleaning and flushing completed (if applicable) |  |  |  |  |
| 8 | Lubrication schedule completed for all rotating equipment |  |  |  |  |
| 9 | All safety devices tested: trips, interlocks, emergency stops, relief valves |  |  |  |  |
| 10 | All isolation valves in correct pre-start position (valve alignment check) |  |  |  |  |
| 11 | SCADA / PLC programming complete and FAT / SAT signed off |  |  |  |  |
| 12 | O&M manuals available on site for all equipment in the system |  |  |  |  |
| 13 | Operator training completed for this system |  |  |  |  |
| 14 | Emergency operating procedures available and briefed |  |  |  |  |
| 15 | Permit to start-up issued (if applicable) |  |  |  |  |

# 3. Safety and Environmental Checks

| No. | Check Item | Yes | No | N/A | Initials |
| --- | --- | --- | --- | --- | --- |
| 1 | Risk assessment for start-up reviewed and briefed to all personnel |  |  |  |  |
| 2 | COSHH assessments available for all process chemicals |  |  |  |  |
| 3 | Spill containment and bunding in place for chemical storage |  |  |  |  |
| 4 | Emergency shower and eye wash stations tested and accessible |  |  |  |  |
| 5 | Fire extinguishers in place and in date |  |  |  |  |
| 6 | Gas detection / atmospheric monitoring operational (if applicable) |  |  |  |  |
| 7 | Confined space entry arrangements in place (if applicable) |  |  |  |  |
| 8 | Exclusion zones established around high-risk start-up activities |  |  |  |  |
| 9 | Noise protection zones identified and signage displayed |  |  |  |  |
| 10 | Environmental permits confirmed in place (discharge, abstraction) |  |  |  |  |
| 11 | Consent to discharge obtained from the regulator (if applicable) |  |  |  |  |
| 12 | First aid provision confirmed and first aiders briefed |  |  |  |  |

# 4. Utility Supplies

| Utility | Available? | Tested? | Supply Details | Initials |
| --- | --- | --- | --- | --- |
| Mains electrical supply | Y / N | Y / N |  |  |
| Standby generator | Y / N | Y / N |  |  |
| UPS supply (for controls) | Y / N | Y / N |  |  |
| Potable water supply | Y / N | Y / N |  |  |
| Raw / process water supply | Y / N | Y / N |  |  |
| Compressed air supply | Y / N | Y / N |  |  |
| Chemical dosing supply | Y / N | Y / N |  |  |
| Drainage and waste connections | Y / N | Y / N |  |  |
| Ventilation / HVAC systems | Y / N | Y / N |  |  |
| Telecommunications / data | Y / N | Y / N |  |  |

# 5. Equipment Pre-Start Verification

| No. | Equipment Tag / Name | SAT Complete? | Rotation Check | Vibration OK? | Alarm Test | Ready? |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |
| 2 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |
| 3 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |
| 4 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |
| 5 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |
| 6 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |
| 7 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |
| 8 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |
| 9 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |
| 10 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |
| 11 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |
| 12 |  | Y/N | CW / CCW | Y/N | Y/N | Y/N |

# 6. Start-Up Sequence

| Step | Action | Completed | Time / Initials |
| --- | --- | --- | --- |
| 1 | Confirm all pre-start prerequisites complete (Section 2 above) | Y/N |  |
| 2 | Confirm safety and environmental checks complete (Section 3 above) | Y/N |  |
| 3 | Confirm all personnel briefed and in position | Y/N |  |
| 4 | Confirm communication channels open (radios tested) | Y/N |  |
| 5 | Open inlet valves / start feed to the process | Y/N |  |
| 6 | Start ancillary systems (chemical dosing, air supply, cooling) | Y/N |  |
| 7 | Start main process equipment in sequence per operating procedure | Y/N |  |
| 8 | Monitor process parameters: flow, level, pressure, temperature | Y/N |  |
| 9 | Verify all alarms and trips function correctly under live conditions | Y/N |  |
| 10 | Confirm SCADA displays and data logging operating correctly | Y/N |  |
| 11 | Check for leaks, abnormal noise, vibration, or overheating | Y/N |  |
| 12 | Record initial operating parameters (Section 7 below) | Y/N |  |
| 13 | Achieve steady-state operation and confirm design duty point | Y/N |  |
| 14 | Handover to operations team (if applicable) | Y/N |  |

# 7. Initial Operating Parameters

| Parameter | Design Value | Measured Value | Within Tolerance? |
| --- | --- | --- | --- |
| Flow rate (l/s or m³/hr) |  |  | Y / N |
| Discharge pressure (bar) |  |  | Y / N |
| Suction pressure (bar) |  |  | Y / N |
| Motor current (A) |  |  | Y / N |
| Motor temperature (°C) |  |  | Y / N |
| Vibration level (mm/s) |  |  | Y / N |
| Bearing temperature (°C) |  |  | Y / N |
| Process level (m or %) |  |  | Y / N |
| pH (if applicable) |  |  | Y / N |
| Dissolved oxygen (if applicable) |  |  | Y / N |
|  |  |  | Y / N |
|  |  |  | Y / N |

# 8. Issues and Snags

| No. | Issue Description | Action Required | Owner | Status |
| --- | --- | --- | --- | --- |
| 1 |  |  |  | Open / Closed |
| 2 |  |  |  | Open / Closed |
| 3 |  |  |  | Open / Closed |
| 4 |  |  |  | Open / Closed |
| 5 |  |  |  | Open / Closed |
| 6 |  |  |  | Open / Closed |
| 7 |  |  |  | Open / Closed |
| 8 |  |  |  | Open / Closed |

# 9. Start-Up Authorisation

This checklist confirms that all pre-start-up prerequisites have been met and the system is safe and ready for initial process start-up. Start-up is authorised by the signatures below.

| Commissioning Engineer |  | Process / Operations Manager |  |
| --- | --- | --- | --- |
| Name: | Print name | Name: | Print name |
| Signature: |  | Signature: |  |
| Date: | DD / MM / YYYY | Date: | DD / MM / YYYY |

| Project Manager |  | H&S Manager |  |
| --- | --- | --- | --- |
| Name: | Print name | Name: | Print name |
| Signature: |  | Signature: |  |
| Date: | DD / MM / YYYY | Date: | DD / MM / YYYY |

# 10. Document Control

| Revision | Date | Description of Change | Author | Approved By |
| --- | --- | --- | --- | --- |
| 01 | DD/MM/YYYY | Initial issue |  |  |
|  | DD/MM/YYYY |  |  |  |
|  | DD/MM/YYYY |  |  |  |