## Weather Action Log
ebrora.com
ADVERSE WEATHER ACTION LOG
Ref: CDM 2015; Met Office Weather Warnings; HSE guidance on seasonal hazards
Project: |  |  |  | Site Manager: |  |  |  | Rev:
No. | Date | Weather Event Type | Met Office Warning Level | Wind Speed (mph) / Temp (°C) / Rainfall (mm) | Affected Work Areas | Works Suspended? (Yes/No) | Time Work Stopped | Time Work Resumed | Actions Taken / Protective Measures | Plant / Equipment Secured? (Yes/No) | Impact on Programme | Recorded By | Reviewed By (Site Manager)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
SUMMARY
Total Events: |  | 0
Works Suspended: |  | 0
Red Warnings: |  | 0
Programme Critical: |  | 0

## Instructions
ebrora.com
INSTRUCTIONS — Adverse Weather Action Log
How to Use This Template
1. Monitor Met Office weather warnings daily and record any events.
2. Select the weather event type and Met Office warning level from dropdowns.
3. Record measured conditions (wind speed, temperature, rainfall) where available.
4. Note which work areas are affected and whether work was suspended.
5. Record times work stopped and resumed, and all protective actions taken.
6. Confirm plant and equipment was secured during adverse weather.
7. Assess the impact on programme and record accordingly.
8. Red Met Office warnings are flagged — consider stopping all outdoor works.
Common Wind Speed Triggers:
>25 mph — review crane operations
>35 mph — suspend crane and MEWP operations
>45 mph — consider stopping all working at height
>55 mph — consider full site shut-down
References:
CDM Regulations 2015
Met Office National Severe Weather Warning Service
HSE guidance on seasonal weather hazards
BS 7121 — Safe Use of Cranes (wind speed limits)