Shutdown Arrangements Plan

For planning and coordinating planned shutdowns, outages, and turnarounds on operational plant and infrastructure

| Document Reference: | SD-PLAN-001 |
| --- | --- |
| Revision: | 0 |
| Date: | DD/MM/YYYY |
| Project Name: | Enter project / asset name |
| Contract Number: | Enter contract number |
| Shutdown Title: | e.g., Annual Maintenance Shutdown, Planned Outage, Tie-In Window |
| Planned Start Date: | DD/MM/YYYY at HH:MM |
| Planned End Date: | DD/MM/YYYY at HH:MM |
| Duration: | days / hours |
| Shutdown Manager: | Enter name and contact |
| Prepared By: | Enter name and role |
| Approved By: | Enter name and role |

1. Shutdown Scope of Work

Describe the scope of work to be completed during the shutdown. Include: systems/assets to be shut down, work packages and disciplines involved, tie-ins to existing systems, modifications, inspections, testing, and commissioning activities. Reference the shutdown work list.

2. Key Roles and Responsibilities

| Role | Name / Organisation | Contact Number |
| --- | --- | --- |
| Shutdown Manager |  |  |
| Shutdown Planner |  |  |
| Isolation Coordinator |  |  |
| Permit Coordinator |  |  |
| Safety Advisor |  |  |
| Operations Representative |  |  |
| Commissioning Manager |  |  |
| Site Manager (Contractor) |  |  |
| Client / Asset Owner Rep |  |  |

3. Shutdown Programme Key Milestones

| No. | Milestone | Planned Date / Time | Actual | Notes |
| --- | --- | --- | --- | --- |
| 1 | Pre-shutdown preparation complete |  |  |  |
| 2 | Plant shutdown / process handover |  |  |  |
| 3 | Isolations applied and verified |  |  |  |
| 4 | Permits issued — shutdown work commences |  |  |  |
| 5 | Critical path work complete |  |  |  |
| 6 | Non-critical work complete |  |  |  |
| 7 | De-isolation and reinstatement |  |  |  |
| 8 | Commissioning and testing |  |  |  |
| 9 | Operational handback / plant restart |  |  |  |
| 10 | Post-shutdown review |  |  |  |

4. Pre-Shutdown Readiness Checklist

| No. | Readiness Requirement | Yes | No | N/A | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | Shutdown scope of work defined and frozen (no scope additions without formal change control) |  |  |  |  |
| 2 | Shutdown programme prepared, resource-loaded, and issued to all parties |  |  |  |  |
| 3 | Critical path identified and communicated to shutdown team |  |  |  |  |
| 4 | All materials, spares, and consumables pre-staged on site and verified against the work list |  |  |  |  |
| 5 | Specialist tools, equipment, and plant pre-ordered and confirmed available for the shutdown dates |  |  |  |  |
| 6 | Scaffolding and access requirements identified and erected before shutdown commences |  |  |  |  |
| 7 | All permits to work pre-planned and permit packs prepared for Day 1 activities |  |  |  |  |
| 8 | Isolation schedules prepared and agreed with operations / asset owner |  |  |  |  |
| 9 | Labour resources confirmed: all trades, supervisors, and management mobilised and inducted |  |  |  |  |
| 10 | Subcontractor contracts awarded and mobilisation plans confirmed |  |  |  |  |
| 11 | Welfare and logistics arrangements confirmed (parking, canteen capacity, changing facilities, tool stores) |  |  |  |  |
| 12 | Safety briefing and shutdown-specific induction prepared and scheduled for all personnel |  |  |  |  |
| 13 | Emergency response arrangements reviewed and scaled for shutdown manning levels |  |  |  |  |
| 14 | Communications plan established (daily meetings schedule, escalation contacts, progress reporting) |  |  |  |  |
| 15 | Contingency plans prepared for key risks (weather, late materials, plant breakdown, scope growth) |  |  |  |  |

5. Isolation Summary

Summarise the isolation strategy for the shutdown. Identify: number of electrical isolations, number of mechanical isolations, key high-risk isolations, coordination requirements between isolation certificates, and the sequence of isolations. Reference the detailed isolation schedule.

| No. | System / Equipment | Isolation Type | Cert. Number | Isolating Authority | Date Applied | Date Removed |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |

6. Resource Plan Summary

| Trade / Resource | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pipefitters / Welders |  |  |  |  |  |  |  |
| Mechanical Fitters |  |  |  |  |  |  |  |
| Electricians |  |  |  |  |  |  |  |
| Instrument Technicians |  |  |  |  |  |  |  |
| Scaffolders |  |  |  |  |  |  |  |
| Crane / Rigging |  |  |  |  |  |  |  |
| General Labour |  |  |  |  |  |  |  |
| Supervision / Management |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |

7. Working Hours and Shift Arrangements

| Day Shift: | e.g., 07:00–19:00 (12 hours) |
| --- | --- |
| Night Shift: | e.g., 19:00–07:00 (12 hours) — if applicable |
| Shift Pattern: | e.g., 2 x 12-hour shifts, 4 on 4 off, continuous |
| Weekend Working: | Yes / No — Specify days and hours |
| Maximum Shift Duration: | 12 hours (fatigue management policy applies) |
| Rest Period Between Shifts: | Minimum 11 hours consecutive rest |

8. Safety Arrangements

Describe the specific safety arrangements for the shutdown including: additional safety supervision, SIMOPS management, emergency response escalation (increased manning), first aid provisions (on-site paramedic if >100 persons), fire watch arrangements, confined space teams, rescue teams, and any additional PPE requirements beyond standard site rules.

9. Commissioning and Handback

Describe the commissioning and handback process including: punch list / snagging process, system reinstatement sequence, leak testing, functional testing, performance testing, and the formal handback process to operations. State the acceptance criteria and who authorises the return to service.

10. Notes / Additional Comments

Enter any additional comments.

Approval and Distribution

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Shutdown Manager |  |  | DD/MM/YYYY |
| Safety Advisor |  |  | DD/MM/YYYY |
| Operations Manager |  |  | DD/MM/YYYY |
| Client / Asset Owner |  |  | DD/MM/YYYY |

Document Control

| Rev. | Date | Author | Description |
| --- | --- | --- | --- |
| 0 | DD/MM/YYYY |  | Initial issue |