Acceleration Proposal

| Proposal Reference: | Enter reference (e.g. ACC-001) |
| --- | --- |
| Revision: | Enter revision number |
| Date: | DD/MM/YYYY |
| Project Name: | Enter project name |
| Contract Number: | Enter contract number |
| Client / Employer: | Enter client name |
| Contract Type: | NEC4 / JCT 2016 / FIDIC / Bespoke |
| Prepared By: | Enter name and role |
| Approved By: | Enter name and role |

# Table of Contents

# 1. Executive Summary

Summarise the acceleration proposal: the reason for acceleration, the programme benefit offered, the cost of acceleration, and the key risks. State whether the acceleration is instructed by the client or proposed by the contractor.

# 2. Background and Reason for Acceleration

| Current Completion Date: | DD/MM/YYYY |
| --- | --- |
| Required / Target Completion Date: | DD/MM/YYYY |
| Time to be Recovered (days/weeks): | Enter number |
| Reason for Acceleration: | Client instruction / Programme recovery / Key Date achievement / Commercial benefit / Third party requirement |
| Contractual Basis: | e.g. NEC4 Cl. 36, JCT Cl. 2.28 (acceleration by agreement), FIDIC Cl. 8.6 |
| Client Instruction Reference: | Enter instruction reference (if client-instructed) |

Provide a narrative description of the circumstances requiring acceleration:

Describe the current programme position, the causes of delay (if recovering), the client’s requirement for earlier completion, and the rationale for the proposed acceleration measures.

# 3. Programme Analysis

| Current Accepted Programme Ref: | Enter programme revision |
| --- | --- |
| Current Planned Completion: | DD/MM/YYYY |
| Accelerated Programme Ref: | Enter accelerated programme revision |
| Accelerated Planned Completion: | DD/MM/YYYY |
| Programme Time Saved: | Enter number of days / weeks |
| Critical Path (Current): | Describe current critical path sequence |
| Critical Path (Accelerated): | Describe how critical path changes under acceleration |

# 4. Proposed Acceleration Measures

Detail all measures proposed to achieve the accelerated completion. Each measure should be described with its individual programme benefit and cost.

| No. | Acceleration Measure | Programme Benefit (days) | Additional Cost (£) | Risk Level | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | Extended working hours (e.g. 12-hour shifts) |  |  | H / M / L |  |
| 2 | Weekend working |  |  | H / M / L |  |
| 3 | Night working |  |  | H / M / L |  |
| 4 | Additional labour resources |  |  | H / M / L |  |
| 5 | Additional plant and equipment |  |  | H / M / L |  |
| 6 | Re-sequencing of activities |  |  | H / M / L |  |
| 7 | Parallel working (activities previously sequential) |  |  | H / M / L |  |
| 8 | Alternative construction methods |  |  | H / M / L |  |
| 9 | Prefabrication / off-site manufacture |  |  | H / M / L |  |
| 10 | Additional subcontractor resources |  |  | H / M / L |  |
| 11 | Fast-track procurement of long-lead items |  |  | H / M / L |  |
| 12 | Reduction of non-critical scope (by agreement) |  |  | H / M / L |  |
|  | TOTAL |  |  |  |  |

# 5. Cost of Acceleration

## 5.1 Additional Labour Costs

| No. | Role / Trade | Rate (£/hr) | Hours | Weeks | Total (£) | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |
|  | Sub-Total |  |  |  |  |  |

## 5.2 Additional Plant and Equipment

| No. | Plant / Equipment | Rate (£/day) | Duration | Qty | Total (£) | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |
|  | Sub-Total |  |  |  |  |  |

## 5.3 Other Acceleration Costs

| No. | Description | Basis | Total (£) | Comments |
| --- | --- | --- | --- | --- |
| 1 | Additional supervision / management |  |  |  |
| 2 | Overtime premium payments |  |  |  |
| 3 | Additional welfare / facilities |  |  |  |
| 4 | Additional temporary lighting (night works) |  |  |  |
| 5 | Noise mitigation / Section 61 consent |  |  |  |
| 6 | Additional testing / commissioning |  |  |  |
| 7 | Transport / travel costs |  |  |  |
| 8 | Subcontractor acceleration costs |  |  |  |
|  | Sub-Total |  |  |  |

## 5.4 Acceleration Cost Summary

| Item | Amount (£) |
| --- | --- |
| Additional Labour |  |
| Additional Plant and Equipment |  |
| Other Acceleration Costs |  |
| Sub-Total Defined Cost |  |
| Fee / Overhead and Profit (%) | Enter % |
| Risk Allowance |  |
| Total Acceleration Cost (excl. VAT) |  |

# 6. Risks and Constraints

Identify the key risks associated with implementing the acceleration measures and any constraints that may affect their success.

| No. | Risk / Constraint | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 |  | H / M / L | H / M / L |  |  |
| 2 |  | H / M / L | H / M / L |  |  |
| 3 |  | H / M / L | H / M / L |  |  |
| 4 |  | H / M / L | H / M / L |  |  |
| 5 |  | H / M / L | H / M / L |  |  |
| 6 |  | H / M / L | H / M / L |  |  |

# 7. Assumptions

List all assumptions underpinning this acceleration proposal. Include assumptions about: availability of additional resources, weather, design information availability, subcontractor cooperation, planning/permit conditions (e.g. Section 61 consent for night works), and any preconditions that must be met before acceleration can commence.

# 8. Health and Safety Considerations

Describe any health and safety implications of the proposed acceleration measures.

Consider: fatigue management for extended/night working, increased interface risks from parallel working, additional traffic management, temporary lighting requirements, noise and vibration impacts on neighbours, welfare provisions for extended hours, and any amendments to the Construction Phase Plan.

# 9. Proposed Terms of Acceptance

| Acceleration Cost (£ excl. VAT): | Enter total from Section 5.4 |
| --- | --- |
| Programme Benefit: | Enter number of days / weeks saved |
| Revised Completion Date: | DD/MM/YYYY |
| Payment Terms: | Describe proposed payment arrangements (monthly, milestone, lump sum) |
| Commencement of Acceleration: | DD/MM/YYYY (or number of days after acceptance) |
| Validity Period of Proposal: | Enter number of days this proposal remains open for acceptance |
| Conditions Precedent: | List any conditions that must be met before acceleration commences |

# 10. Proposal Sign-Off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared By: |  |  |  |
| Planner: |  |  |  |
| Commercial Manager: |  |  |  |
| Project Director: |  |  |  |

Client / Project Manager Response

| Proposal Response: | Accepted / Accepted with Amendments / Rejected |
| --- | --- |
| Amendments (if any): | Enter details of amendments |
| Agreed Acceleration Cost (£): | Enter agreed amount |
| Agreed Revised Completion Date: | DD/MM/YYYY |

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Manager / Client: |  |  |  |

# 11. Document Control

| Revision | Date | Description | Author | Approved By |
| --- | --- | --- | --- | --- |