Time Impact Analysis Template

| Document Reference: | Enter document reference |
| --- | --- |
| Revision: | Enter revision number |
| Date: | DD/MM/YYYY |
| Project Name: | Enter project name |
| Contract Number: | Enter contract number |
| Client: | Enter client name |
| Contract Type: | NEC / JCT / FIDIC / Bespoke |
| Delay Event Reference: | Enter CE / variation / instruction reference |
| Prepared By: | Enter name and role |
| Approved By: | Enter name and role |

# Table of Contents

# 1. Introduction

This Time Impact Analysis (TIA) has been prepared to demonstrate the impact of a delay event on the project programme. The TIA methodology inserts the delay event into the programme as it stood immediately before the event occurred, and measures the resulting change to the predicted completion date.

The TIA is a prospective (or contemporaneous) delay analysis technique recognised by the Society of Construction Law Delay and Disruption Protocol (2nd Edition, 2017) and is commonly used under NEC, JCT, and FIDIC forms of contract in the UK construction industry.

# 2. Delay Event Description

| Delay Event Reference: | Enter reference (e.g. CE-001, VI-012, EOT-003) |
| --- | --- |
| Event Title: | Enter brief descriptive title |
| Date Event Occurred / Notified: | DD/MM/YYYY |
| Date Event Ceased / Expected to Cease: | DD/MM/YYYY |
| Duration of Event (calendar days): | Enter number of calendar days |
| Duration of Event (working days): | Enter number of working days |
| Contractual Basis for Claim: | e.g. NEC Clause 60.1(1), JCT Clause 2.29.1, FIDIC Clause 8.5 |
| Relevant Contract Clause: | Enter specific clause reference |
| Employer Risk / Contractor Risk: | State which party bears the risk under the contract |

Detailed Description of Event

Provide a detailed factual narrative of the delay event. Describe what happened, when, where, and why. Reference supporting documentation (correspondence, drawings, instructions, photographs, diaries). State the cause, the effect on the works, and the activities directly impacted.

# 3. Pre-Impact Programme (Baseline)

Identify the programme version used as the baseline for this analysis. This should be the accepted/approved programme immediately prior to the delay event.

| Programme Title: | Enter programme name |
| --- | --- |
| Programme Revision: | Enter revision reference |
| Data Date: | DD/MM/YYYY (the status date of the programme) |
| Completion Date (Pre-Impact): | DD/MM/YYYY |
| Critical Path (Pre-Impact): | Describe the critical path sequence prior to the delay event |
| Longest Path Method Used: | Yes / No |
| Software Used: | e.g. Primavera P6, Asta Powerproject, Microsoft Project |

# 4. Impacted Activities

Identify all programme activities directly affected by the delay event. Record the original planned dates, the impact of the event, and the revised dates.

| No. | Activity Description | Original Start | Original Finish | Impacted Start | Impacted Finish | Delay (days) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY |  |
| 2 |  | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY |  |
| 3 |  | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY |  |
| 4 |  | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY |  |
| 5 |  | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY |  |
| 6 |  | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY |  |
| 7 |  | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY |  |
| 8 |  | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY | DD/MM/YYYY |  |

# 5. Delay Event Insertion

Describe how the delay event has been modelled in the programme. Detail the activities added, logic links modified, duration changes, and constraints applied.

## 5.1 Activities Added to Programme

| No. | Activity Added | Duration (days) | Start | Finish | Predecessor | Successor |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  | DD/MM/YYYY | DD/MM/YYYY |  |  |
| 2 |  |  | DD/MM/YYYY | DD/MM/YYYY |  |  |
| 3 |  |  | DD/MM/YYYY | DD/MM/YYYY |  |  |
| 4 |  |  | DD/MM/YYYY | DD/MM/YYYY |  |  |

## 5.2 Logic Links Modified

| No. | Original Link | Modified Link | Reason for Change | Type (FS/SS/FF/SF) |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |

# 6. Analysis Results

| Pre-Impact Completion Date: | DD/MM/YYYY |
| --- | --- |
| Post-Impact Completion Date: | DD/MM/YYYY |
| Net Delay to Completion (calendar days): | Enter number of calendar days |
| Net Delay to Completion (working days): | Enter number of working days |
| Critical Path Changed: | Yes / No – if yes, describe new critical path |
| Float Consumed (days): | Enter total float consumed by the event |
| Concurrent Delay Identified: | Yes / No – if yes, describe and apportion |

Narrative of Results

Provide a narrative explanation of the analysis results. Explain how the delay event impacts the critical path and completion date. Address any issues of concurrency, mitigation, or acceleration. Reference programme extracts appended to this document.

# 7. Mitigation Measures

Describe any mitigation measures that have been or could be implemented to reduce the impact of the delay. Distinguish between measures already taken and those proposed.

Describe mitigation measures: re-sequencing of activities, acceleration proposals, additional resources, revised methodology, extended working hours, etc. State whether these measures have been implemented or are proposed, and the anticipated programme benefit.

# 8. Extension of Time Entitlement Summary

| Extension of Time Claimed (days): | Enter number of working/calendar days |
| --- | --- |
| Revised Completion Date Sought: | DD/MM/YYYY |
| Contractual Basis: | Reference specific contract clause |
| Associated Cost Claim: | Yes / No – if yes, reference separate cost submission |

# 9. Supporting Documentation

| No. | Document Title | Reference | Date |
| --- | --- | --- | --- |
| 1 | e.g. Pre-impact programme, post-impact programme, correspondence, site diary |  | DD/MM/YYYY |
| 2 | e.g. Pre-impact programme, post-impact programme, correspondence, site diary |  | DD/MM/YYYY |
| 3 | e.g. Pre-impact programme, post-impact programme, correspondence, site diary |  | DD/MM/YYYY |
| 4 | e.g. Pre-impact programme, post-impact programme, correspondence, site diary |  | DD/MM/YYYY |
| 5 | e.g. Pre-impact programme, post-impact programme, correspondence, site diary |  | DD/MM/YYYY |
| 6 | e.g. Pre-impact programme, post-impact programme, correspondence, site diary |  | DD/MM/YYYY |
| 7 | e.g. Pre-impact programme, post-impact programme, correspondence, site diary |  | DD/MM/YYYY |
| 8 | e.g. Pre-impact programme, post-impact programme, correspondence, site diary |  | DD/MM/YYYY |

# 10. Report Sign-Off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Prepared By: |  |  |  |
| Planner / Programmer: |  |  |  |
| Commercial Manager: |  |  |  |
| Project Manager: |  |  |  |

# 11. Document Control

| Revision | Date | Description | Author | Approved By |
| --- | --- | --- | --- | --- |